Project Implementation Plan

2013-2014

Pauri Garhwal District

Uttrakhand

ACKNOWLEDGEMENT

To achieve the better health and well being for the masses the relentless efforts could not be finish without the support collaborating efforts of the whole Medical team from CHC/PHC to District. Preparation of this District Action Plan under National Rural Health Mission. It would not be possible without much needed cooperation provided  by Dy. CMO, NRHM &  as a whole DPMU & BMPU unit.

Last, but not the least we appreciate the technical guidance which was provided to us by Future Group (HPP) in Last year (2012-13) planning process our DHAP and also to all who have been closely associated with the team for accomplishment of the task and brought such an important document plan.

Chief Medical Officer

Pauri Garhwal

INDEX

District Pauri Garhwal

| Serial No | Contents | Page No. |
| --- | --- | --- |
|  | Introduction | 6 |
|  | Goals And Objectives for District Rural Health Mission | 7 |
|  | Background and Current Status | 9 |
|  | Situation Analysis | 11 |
|  | Health Indicators of the District | 23 |
|  | Process of Plan Preparation | 24 |
| Part A | Reproductive and Child Health (RCH) II | 25 |
|  | - Maternal Health | 27 |
|  | - Child health | 47 |
|  | - Fertility & Family planning | 56 |
|  | - ARSH | 64 |
|  | - Urban Health Project | 67 |
| Part B | NRHM Additionalities | 71 |
| Part C | Immunisation | 93 |
|  | Inter-Sectoral Convergence | 98 |
|  | Infrastructure | 102 |
|  | Bio Medical Waste Management | 104 |
|  | Procurement and Logistics | 105 |
|  | Monitoring and Evaluation | 108 |
|  | Budget Abstract | 110 |

1.   INTRODUCTION

The National Rural Health Mission (NRHM) has been launched in Uttrakhand with a view to bring architectural correction of the health system to enable it to effectively handle increased allocations and promote policies that strengthen public health management and service delivery. It aims to improve the health status of the people, especially those who live in the villages/ inaccessible areas. The vision is to provide universal access to equitable, affordable and quality health care services which is accountable at the same time responding to the needs of the people. The programme is funded by Government of India and State Government. NRHM covers the entire country, with special focus on some states where the challenge of strengthening poor public health systems and thereby improve key health indicators is the greatest. The mission envisions targeting especially rural/ tribal people, poor women and children for providing equitable, affordable, accountable and effective primary health care. DHAP contains situational analysis of the district, objectives and interventions, work plan and budgets and an M&E plan including training plan, BCC plan and Logistics systems plan. After formulation of each DHAP it will be appraised and approved at state level and will be guiding document for implementation, monitoring & evaluation of NRHM activities in the district..

District Pauri Garhwal has successfully managed to gear its efforts towards improving service provisions at the grass roots level in spite of its limitations, in terms of availability of skilled manpower and difficult geographical terrain. With ASHA in place demand for service has certainly increased. District has seen a remarkable shift from domiciliary to institutional delivery and the statistics will certainly improve once we strengthen our existing LI , LII, LIII and also develop our present institutes into LI, LII & LIII .

District Pauri has completed the selection of ASHAs across district. District has already completed Seventh modules in which focus is on HBNC which would be of great help to rural population residing in remote locations..

Finally, in the district consultation larger range of stakeholders from different departments, attempted to examine & work out strategies in context of feasibility & viability especially for increasing accessibility and quality of services and come up with district specific comprehensive strategies as well as tentative time frame to achieve the goals & objectives. The other stakeholders involved in formulation of these activities includes ICDS, Water & sanitation departments/SWAJAL, Education, PRIs, civil societies etc.

2. GOALS AND OBJECTIVES OF NRHM

GOALS:-

The goal of National Rural Health Mission is to improve the availability of and access to quality health care by the people especially for those residing in rural areas, the poor, women and children. The main aim of National Rural Health Mission is to provide accessible, affordable, accountable, effective and reliable primary health care,

Especially to poor and vulnerable sections of the population. It aims at reduction in Infant Mortality Rate and Maternal Mortality Ratio, universal access to public health services such as women's health, child health, water, sanitation and hygiene, immunization and nutrition, prevention and control of communicable and non communicable diseases including locally endemic diseases; access to integrated comprehensive primary health care; population stabilization; gender and demographic balance; revitalize local health traditions and mainstream AYUSH and promotion of healthy lifestyle.

OBJECTIVES OF THE MISSION:-

- Reduction in Infant Mortality Rate.

- Reduction in Maternal Mortality Rate.

- Universal access to public health services- Women’s health, Child health, drinking water, hygiene, sanitation ,nutrition and universal immunization.

- Prevention and control of communicable and non-communicable diseases.

- Access to integrated comprehensive primary healthcare.

- Ensuring population stabilization, gender and demographic balance.

- Revitalize local health traditions and mainstream AYUSH.

- Promotion of healthy life styles.

OBJECTIVES OF DISTRICT PROGRAMME IMPLEMENTATION PLAN UNDER NRHM:-

The District programme implementation plan under the NRHM shall pursue the following objectives by the year 2013-14.

- Reduction in Infant Mortality Rate from 43 (AHS 2011) to 40 per 1000 live births.

- To reduce Maternal Mortality Ratio from 190 (AHS 2011) to less than 180 per 1,00,000 live births.

- Total Fertility Rate is to be reduced from current 2.4 (AHS 2011) to 2.3.

- 04 PHCs (APHC Satpuli, APHC Chakisain, APHC Chelusain, APHC Dumakoot)  and 15 Sub centres will be converted into functional delivery Points. Strengthening of existing 08 Functional Delivery points and 14 Delivery Points will be done.

- The proportion of institutional deliveries has increased to 60% 2012 and we are planning to increase it by 65% in 2013-2014.

- Plan for full utilization of schemes like JSSK & KKS.

- To improve outreach of health services through Mobile Medical Units in difficult to reach areas and disadvantaged population groups.

- Leprosy Prevalence Rate – reduce from 0.5 per 10,000 in 2013-14  to 0.3 per 10,000 thereafter.

- Tuberculosis DOTS series - maintain 85% cure rate through entire Mission Period and also sustain planned case detection rate.

- Access to appropriate and guaranteed hospital care through assured availability of doctors, drugs and quality services at PHC/CHC level and 24x7.

3. BACKGROUND AND CURRRENT STATUS

Geographic location:

District Pauri Garhwal which is surrounded by the districts of Chamoli, Almora, Nainital, Bijnor, Haridwar, Dehradun, Rudraprayag and Tehri Garhwal, offers a panoramic view of the great Himalayas form its towns and villages. The majestic Himalaya and its mountain range can be seen from anywhere in the district.
The Pauri City which is situated at an altitude of 1814 Mts. above the sea-level on the northern slopes of Kandoliya hills is the headquarters of the District Pauri Garhwal and the Garhwal Division. Headquarters of all Govt. departments are located in the city Pauri. District Pauri has been identified as the basic coordination unit for planning and administration of Health.

Socio-demographic profile of the Pauri :

The District has Nine Tehsil and 15 Blocks. The district administrative divisions comprise of development blocks. 118 Nayay Panchyat,1208 Gram Sabha 3473 revenue villages and six towns. 59.19 percent of villages in the district have a population size of less than 500. The density of population is 129 persons per square kilometres. The Total population of the district according to the 2011 census was 6.86 lakhs.The scheduled caste population varies between 13-17 percent. The sex ratio of population was 1103 females per 1000 males while it was 963 for the state as a whole. The overall literacy level of pauri was higher (82.59) than the state literacy rate of 79.6 percent. As expected, female literacy level was lower than male literacy level in the district, In regard to caste, 96.61 percent of the population was Hindus and 15.53 percent households belonged to SC/ST caste groups. About 46 percent of population resides in Pucca households and 61 percent households have access to tap water.

District Profile of Pauri Garhwal

| S/No | Background Characteristic | Number | % to Total |
| --- | --- | --- | --- |
| 1 | Geographic Area (in Sq Kms) | 3689 | -- |
| 2 | Number of Blocks | 15 | -- |
| 3 | Number of Tehsils | 9 |  |
| 4 | No of Villages (2011 Census) | 3473 | -- |
| 5 | Number of towns | 06 |  |
| 6 | Total Population(2011) -Males -Females - Urban Population - Rural Population Growth Rate(2001-2011) -Urban -Rural | 686527 326406 360121 112680 573847 | 16.41 83.59 -1.51 25.37 -5.49 |
| 7 | Sex Ratio(F/M* 1000) Sex Ratio(0 to 6 yr) | 1103 929 |  |
|  | Decadal growth rate |  | -1.51 |
|  | Birth Rate |  | 19.5 |
|  | Death Rate |  | 6.7 |
| 8 | Density-per sq. km. | 129 |  |
| 9 | Literacy Rate -Male -Female |  | 82.59 93.18 73.26 |
| 10 | SC/ST population | 108247 | 15.53 |
| 11 | Length of road per 100 sq. km.* | 44 sq. km. | -- |
| 12 | % residing in Pucca households* | 145591 | 46 |
| 13 | % of households having drinking water facility (tap) | -- | 61 |

4. SITUATION ANALYSIS:

Public Health Facilities and Functionalities:

The service utilization is very low because of inadequate human resource and sparsely populated areas, for different aspects of health care. There are significant differences between the urban and rural areas. This could also be attributed to the difficult terrain and problems of mobility faced by the service providers. The access to services is a major problem in both Upper and Middle Himalayas.

Further the vacancy position of the personnel in the various facilities is also high despite the strategy of contract appointment adopted by the government. The availability of personnel is also an important factor in determining the utilization of services. The educational levels also have a significant impact on the utilization of services, as has been the case in the antenatal services Deliveries and child immunization. The regional variations are significant and have to be factored into the development of strategy for the district.

Sub-Centers, district allopathic dispensaries, Additional Primary Health Centers, Block PHCs, and Community Health Centers provide health and reproductive Health services including family planning in the rural areas. The following Table provides an overview of the situation in the district Pauri in terms of the facilities available.

Health Infrastructure:

| Health Facility | Number of Institutions |
| --- | --- |
| District Hospitals | 1 |
| Female Hospitals | 1 |
| Sub District Hospital | 2 |
| Medical College Cum Base Hospital | 1 |
| PPC District | 1 |
| PPC Tehsil | 2 |
| CHC | 5 |
| PHC | 10 |
| APHC | 20 |
| State Allopathic Dispensary | 67 |
| Sub Center | 218 +22 MCH+21 AAG |
| Ayurvedic Dispensary | 74 |
| Homeopathic Dispensary | 7 |
| TB Clinic | 1 |

Bed Capacity of District Pauri Garhwal

| S.No | Institute Name | Capacity |
| --- | --- | --- |
| 1. | District Hospital | 102 |
| 2. | Female Hospital | 30 |
| 3. | Base Hospital | 350 |
| 4. | Combined Hospital Srinagar | 54 |
| 5. | Kotdwara Combined Hospital | 104 |
| 6. | CHC | 30*5 =150 |
| 7. | PHC | 10*4=40 |
| 8. | APHC | 17*4=68 |

First Referral Units in Pauri District:

| Functionality of CHCs , PHCs (24X7) (in terms of availability of critical staff position) |  |  |
| --- | --- | --- |
| Critical Staff | No. of facilities | Names of CHCs/PHCs |
| No of CHCs proposed for FRU | 3 | Pabau , Bironkhal & Thailisian |
| No. of CHC/PHC/APHC Functioning as 24X7 | 16 | Dumakot, Rikhnikhal, Baijro, Satpuli, Khirsu, Chalusain, Pokhal, Patisen, Pokhra, Dugadda, Dadamandi, Jahrikhal, Kot, Yamkeshwar, Ghandiyal, Nainidanda & Chakisen |
| Proposed 24 x7 | 04 | Badiyar Gaon, Kimsar, Siroli & Paithani |
| Ob. & Gy. specialists, | - | NIL |
| Paediatrician | 1 | Bironkhal |
| Anaesthetist (either qualified or trained) at identified FRUs | 3 | 3 (short course) Bironkhal Pabau, Rikhnikhal |
| Availability of a Anaesthetist in proposed FRUs | 2 | Bironkhal Pabau, |

Block-Wise Coverage of Public Health Institutions in Pauri Garhwal :

| S/No | Block | Population Coverage | District /Sub District Hospital/CHCs | Number of PHCs/APHCs | Number of SCs |
| --- | --- | --- | --- | --- | --- |
| 1 | Parsundakhal- Pauri | 59577 | 2 | 3 | 14 |
| 2 | Kot | 30721 |  | 2 | 14 |
| 3 | Khirsu | 48484 | 2 | 1 | 9 |
| 4 | Ghandiyal | 33884 | 1 | 1 | 15 |
| 5 | Pabau | 37694 | 1 | 1 | 16 |
| 6 | Thailisain | 62421 | 1 | 3 | 15 |
| 7 | Patisain | 38837 |  | 2 | 16 |
| 8 | Pokhra | 31461 |  | 1 | 14 |
| 9 | Bironkhal | 54350 | 1 | 2 | 16 |
| 10 | Nainidanda | 45910 | 1 | 1 | 14 |
| 11 | Dugadda | 149094 | 1 | 3 | 17 |
| 12 | Dadamandi | 43551 | - | 4 | 15 |
| 13 | Yamkeshwar | 50660 | - | 2 | 15 |
| 14 | Jaiharikhal | 42549 | - | 2 | 14 |
| 15 | Rikhnikhal | 34745 | - | 2 | 14 |

Human Resource in the District:

The staffing pattern as has been sanctioned for the different categories of facilities has been taken to analyze the operational or fully functional nature of the facilities. Nearly half of regular sanctioned positions of male medical officers are vacant. This problem still persists, as the experiment of having male medical officers on contractual basis has not been a successful venture. In case of LMOs nearly 50 percent of the positions are vacant. Half of medical officers-community health is vacant. There are also a large number of vacancies in case of staff nurses, lab technicians, male workers and male supervisors. As for the shortage of ANMs, this is going to increase under the norm of two ANMs per Sub Center under NRHM.

Staff Position at PHC/CHC

| S.No. | Staff |  | Sanctioned | In position | Contractual | Total in Position | Vacant |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Chief Medical Officer |  | 1 | 1 | - | 1 |  |
| 2 | Dy Chief Medical Officer |  | 6 | 1 | - | 1 | 5 |
| 3 | CMSs |  | 3 | 2 |  | 2 | 1 |
| 4 | Medical Superintendent |  | 1 | 1 |  | 1 | 0 |
| 5 | Male Medical Officers | Ordinary grade | 119 | 42 | 26 Ayurved 5 Allopathic | 73 | 46 |
|  |  | Child specialist | 4 | 1 |  | 1 | 3 |
|  |  | Physician | 5 | 0 | 0 | 0 | 5 |
|  |  | Anaesthetic | 1 | 0 |  | 0 | 1 |
|  |  | Radiologist | 4 | 0 |  | 0 | 3 |
|  |  | Dentist | 4 | 2 | 1 | 3 | 1 |
|  |  | Pathologist | 2 | 0 |  | 0 | 2 |
|  |  | Surgeon | 5 | 0 | 0 | 0 | 5 |
| 6 | Lady Medical Officer | Lady Doctor | 31 | 7 | 1 |  | 23 |
| 7 | Lab technician |  | 15 | 11 | 0 | 11 | 4 |
| 8 | Chief pharmasist |  | 6 | 2 |  | 2 | 4 |
| 9 | Drug Inspector |  | 1 | 0 |  | 0 | 1 |
| 10 | LHV |  | 49 | 43 |  | 43 | 6 |
| 11 | Pharmacists |  | 184 | 158 |  | 158 | 26 |
| 12 | ANMs |  | 280 | 230 | 18 | 248 | 32 |
| 13 | ASHA |  | 945 | 945 | 945 | 945 | 0 |
| 14 | Drivers |  | 25 | 18 |  | 18 | 7 |

It can be observed that there are considerable vacant positions in critical positions especially at the senior management levels and in terms of availability of doctors, ANMs, Male workers and supervisory staff. There are several other vacancies in the department and what has been projected here is the critical position related to RCH.

Status of ANM’s Posted at Sub Centers of Pauri Garhwal:

| S/No | Block | Sanctioned | In-Position |
| --- | --- | --- | --- |
| 1 | Pauri | 21 | 17 |
| 2 | Kot | 17 | 17 |
| 3 | Khirsu | 21 | 11 |
| 4 | Ghandiyal | 18 | 17 |
| 5 | Pabau | 19 | 18 |
| 6 | Thailisain | 18 | 16 |
| 7 | Patisain | 19 | 18 |
| 8 | Pokhra | 16 | 14 |
| 9 | Bironkhal | 19 | 16 |
| 10 | Nainidanda | 17 | 15 |
| 11 | Dugadda | 26 | 21 |
| 12 | Dadamandi | 20 | 19 |
| 13 | Yamkeshwar | 18 | 17 |
| 14 | Jaiharikhal | 17 | 16 |
| 15 | Rikhnikhal | 17 | 16 |
|  |  | 280 | 248 |

Vehicles with Health Department of Pauri Garhwal:

In Regard to Vehicles in the district, there are 36 of them. 33 Vehicles are presently on road and in good condition, and 3 are condemned. All the CHC/PHS has there own ambulances. Also 03 rented Bolero’s are with School Health Team.

| S.No | Type of Vehicle | No of Vehicles | On Road/ Off Road | Repair Request |
| --- | --- | --- | --- | --- |
| 1. | Ambassador | 1 | On road | - |
| 2. | Ambulance | 22 | 20-On road/2-Off road | 2-Condemn |
| 3. | Sumo | 3 | 3-On road | - |
| 4. | Gypsy | 4 | 4-On road | - |
| 5. | Mini Bus | 3 | 3 On road(1 Shifted to Medical college) | - |
| 6. | Jeep | 2 | 1-On road/1-Off road | 1-Condemn |
| 7. | Vaccine Vehicle | 1 | On road | - |
| Total Vehicles |  | 36 |  |  |

Beside these Vehicles, The new innovative EMRI ‘dial 108 scheme’, launched in 2008 to provide relief to people in distress in Uttarakhand,  has attracted a lot of attention, with the government claiming that it has become very useful in the hill state having tough terrains and long serpentine roads.  The scheme was launched in collaboration with emergency management and research institute (EMRI), a private company.

Under the scheme, EMRI, as the nodal agency, has been provided ambulances, equipped with paramedical staffs, life saving drugs, oxygen cylinders and first-aid material. Presently in district Pauri number of Ambulances under this scheme is 16. Which are providing 24*7 services throughout the district. Beside that 11 vehicles are providing Drop Back services under Khusiyon Ki Sawari Scheme.

Panchayat Raj Institution:

Uttrakhand has three-tier Panchayat system. The three tiers are:

- Zilla Panchayat (District Panchayat)

- Kshetra Panchayat (Block Panchayat)

- Gram Panchayat (Village Panchayat)

Elections to the Panchayat Raj Institutions have been held and are now functional. Most of the institutions as per the 73rd amendment have one-third of the seats reserved for women. Pauri Garhwal district has 48 Zila Parishad members of which seven are females. Likewise, there are 15 kshetra Panchayat in the district having 446 members, further the district has 1208 gram Sabhas 3487 village Panchayat members. Each village Panchayat on an average has six members. Health and Welfare Committees have been constituted at gram Panchayat level and has 6 members with gram pradhan as chairperson. The other five members are drawn to represent women, scheduled castes, backward classes and general population. Similarly there are Health and Welfare committees constituted at Kshetra Panchayat and Zila Parishad level. Medical, Health, family welfare, social welfare, women empowerment and child development and welfare of scheduled castes and tribes are subjects given to these committees; these committees have been constituted but are not fully functional.

Non Government Organizations:

- Pauri Garhwal has many active NGOs working in the area of development. These NGO’s have presence in the interior regions of the district and have developed a rapport with the community. They are presently covering the different blocks of the district and four of them are actively working in the area of health. They are:

- Setu Sansthan (Pabau).

- Astha sewa sansthan (Bungidhar).

- Dalio Ka Dagariya (Nanidanda).

- Nehru Yuya Kendara (Pauri).

- These NGOs apart from development activities are implementing health intervention programmes at the block level. The health department coordinates with them for campaigns concerning the national programmes but not on a regular basis. The strength of these NGOs is in community mobilization and therefore efforts should be made to evolve partnership so that awareness and access to health services can be improved.

Besides these other NGOs actively involved in health are:

- Society for Rural Technology, Kotdwar

- Institute for Development Support, Pauri

- Jan Chetna Kendra, Srinagar

- Rural Hill Development & Services Society, Kotdwara

- Sumati Gram Utthan Training Institute, Kotdwara

- Sachitananda Social Institute

- Karuna Samaj Sewa Sansthan

- Gangothri Dham Seva Sansthan

- Paraz , Pauri Garhwal

HEALTH INDICATORS OF THE DISTRICT

Selected Socio-Cultural indicators for the district:-                               Source: Census 2011

| Indicators | Status |
| --- | --- |
| Literacy Rate Male Female | 82.59 93.18 73.26 |
| Sex Ratio | 1103 |
| Age at marriage < 18 years | 3.2 % ( DLHS 3)) |

Selected RCH Indicators of Pauri

| District Health Indicators |  |  |
| --- | --- | --- |
| 1 | Decadal Growth Rate | -1.51% (Census 2011) |
| 2 | Birth rate | 19.5/1000 (AHS 2011) |
| 3 | Death rate | 6.7/1000 (AHS 2011) |
| 4 | IMR | 43/1000 (AHS 2011) |
| 5 | Sex ratio | 1103/1000 (Census 2011) |
| 6 | MMR | 190/lac (AHS 2011) |
| 6 | CPR | 46.3% (DLHS 3) |
| 7 | TFR | 2.4 AHS |
| 8 | Institutional delivery | 60% (HMIS.) |

5. REPRODUCTIVE AND CHILD HEALTH (RCH) II

PART – A

REPRODUCTIVE AND CHILD HEALTH –II

Rationale

In India, one woman dies every five minutes and every year, more than half a million women die as the result of complications of pregnancy and childbirth. Over 80% of all maternal deaths are due to abortion, hypertensive disorders, haemorrhage, obstructed labour and infections. For the most part, the interventions needed to prevent such deaths are well conceived. What is lacking, however, is the ability to implement them in resource - constrained settings. There is a need for better information about the incidence, determinants, long-term consequences and prevention/management of hypertensive disorders of pregnancy, intrauterine growth retardation that account for a large proportion of morbidity and mortality. There is a need to evaluate the determinants of the attitude and practices of women in seeking, health care during pregnancy and childbirth as well as to identify and implement effective approaches for overcoming barriers to use of health care services.

Maternal care has been a priority with the state health department, but gains in maternal survival have not been as much as expected. Problems of access, availability and utilization of the health services are further compounded by the difficult terrains and cultural practices in many parts of the state. In addition, the status of women in the state, reflected in low levels of literacy and limited autonomy further limit the care available to them.

Vision Mission

To provide equitable RCH services in particular and health services in general, in a mission mode, with the objective of bridging the spatial variations and achieving the goals set out in the state policy specifically and national policies at large, by improving accessibility to quality services by improved and strengthened infrastructure facilities, through a comprehensive approach through partnerships with private and civil society organizations, increasing public health investments, reducing gender discrimination and involving elected representatives and community at large.

Objectives

Following are our States objectives which our District would strive to achieve so as to make Uttarakhand achieve its goals.

- Reduce MMR from the present level of 190 (AHS 2011 Survey) to below 180.

- Reduce IMR from the present level of 43 (AHS 2011 Survey) per 1000 live births to 40

- To reduce the TFR from the current level of 2.4 to 2.3.

- Increase modern CPR from the present level of 57.7% to 70%

1.	MATERNAL HEALTH

Utilization of maternal health services in Pauri Garhwal district is low and majority of women depend on public health facilities for services. Women who had not utilized ANC services mentioned that they did not feel the need to avail ANC services. Though women were aware of pregnancy seeking care was negligible and those who sought visited a private doctor. Deliveries in Pauri Garhwal mainly take place at home that are attended by untrained persons and place of delivery are a matter of concern. Emergency obstetric facility is limited in the district and available only at the district hospital while basic obstetric care in four facilities. Women hardly seek postnatal services and ANM rarely visit them for postnatal services. On the whole, awareness about the various services and social customs and traditional practices of the community govern/impede utilization of either availing ANC or Postnatal/post delivery services.

Source : AHS 2011

| Indicator | Pauri | Uttarakhand |
| --- | --- | --- |
| Mothers who had at least 01 Ante-Natal care visits during the last pregnancy (%) | 88.1 | 84.4 |
| Mothers who had at least 3 Ante-Natal care visits during the last pregnancy (%) | 47.4 | 52.3 |
| Mothers who got at least one TT injection when during pregnancy (%) | 87.3 | 83.6 |
| Institutional births (%) | 52.8 | 50.5 |
| Delivery at home assisted by a doctor/nurse /LHV/ANM(%) | 18.3 | 32.0 |
| Mothers who received post natal care within 48 hours of delivery of their last child (%) | 59.6 | 59.1 |

Situational Analysis:

Maternal Health Indicators:-                                                                           HMIS Data Sources:

| Activity | (2006-2007) | (2007-2008) | (2008-2009) | (2009-2010) | (2010-11) | (2011-2012) | (2012-13) (Oct) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ANC (T.T) | 12807 | 12409 | 12733 | 12326 | 10053 | 9947 | 6353 (78% ) |
| 3 ANC Check UP | - | 7344 | 8105 | 7365 | 9032 | 8285 | 4490 |
| Mothers consumed IFA for 90 days during Pregnancy | 11128 | 4827 | 4979 | 15631 | 18163 | 7766 | 6359(78% ) |
| Institutional Deliveries | 2954 | 4429 | 6138 | 6990 | 7292 (293 Priv) | 7768 (368Pri) | 4798 (264) (62%) |
| Home Deliveries | 7189 | 5990 | 5289 | 5040 | 4126 | 3007 | 1448 |
| ANC Registration | 12541 | 12471 | 13256 | 12326 | 13238 | 15390 | 10630 (120%) |

Drop Back Achievement:-

| S.No | HOSPITAL | Total Drop back |
| --- | --- | --- |
| 1 | CHC KOTDWAR | 541 |
| 2 | HNB BASE HOSPITAL SRIKOT | 421 |
| 3 | DISTRICT FEMALE HOSPITAL PAURI | 264 |
| 4 | CHC THALISAIN | 94 |
| 5 | PHC PATISAIN | 102 |
| 6 | CHC RIKHINIKHAL | 55 |
| 7 | ADD PHC SATPULI | 35 |
| 8 | PHC KHIRSU | 21 |
| 9 | CHC PAVO | 36 |
| 10 | PHC DUGGADA | 15 |
| 11 | PHC JEHRIKHAL | 24 |
| 12 | CHC BIROKHAL | 8 |
| 13 | ADD PHC POKHAL | 4 |
| 14 | PHC CHAKISAIN | 4 |
| 15 | PHC DADAMANDI | 8 |
| 16 | PHC DHUMAKOT | 1 |
| 17 | CANTT HOSPITAL LANSEDOWNE | 11 |
| 18 | PHC PARSUNDAKHAL | 2 |
| 19 | CHC NAINIDANDA | 0 |
| 20 | TOTAL | 1646 |

SWOT ANALYSIS MATERNAL HEALTH:

STRENGTH:

- Adequate Infrastructure at CHC/PHC with well Maintained OT’s & Labour Room.

- JSSK & KKS Schemes.

- Sufficient no of ANM/Paramedical staff at field level.

- Sufficient no of ASHA’s/SSS at field level.

- Sufficient funding through NRHM.

- MHV & MMU running in district.

- Referral System is adequate with 16 EMRI 108 & 22 Ambulances in the district.

- HMIS is fully functional while MCTS system is picking pace.

- DARC (945 Asha, 57 facilitator, 7 block coordinator)

WEAKNESS:

- Low institutional deliveries 52.8%  (AHS 2011).

- Total ANC registration only 75.8% (DLHS 3)

- No of sub centers (218) sufficient but only 77 in gov building & only 17 having labour room.

- Lack of specialist & MO’s ( Espl. LMO)

    - C-section facility not even in DH pauri.

Lack of facilities with for emergency obstetric care.

- Training status is poor.

    - Only 28 SBA trained

    - Only 3 EmOC trained in district.

    - 15 doctors trained in MVA but are not utilized properly.

- Blood bank/blood storage facility inadequate.

- Lack of Investigation facilities at PHC/CHC level.

- Irregular supply of drugs.

- Staff not residing at place of work.

- POL problem for Ambulances.

- Inadequate MDR reporting (4 reported till october).

- Lack of Motivation among staff.

OPPURTUNITIES:

- High literacy rate among women.

- 96.8 % women marrying above legal age of marriage.

- AWW, Mahilamangal dal, NGO’s.

- High dependency on public sector.

- Aid can be received from MP/MLA etc.

- VHSC’s and EMRI 108 services.

- Private facilities at kotdwara can be accredited for Maternal health issues

THREATS:

- Low sex ratio 969 (0 to 6 year).

- Difficult geographical terrain.

- Communication problem.

- Female domination (Saas Bahu relation)

- Natural disaster.

- Unregistered medical practioner.

- Political Interferences.

GOAL FOR MATERNAL HEALTH

To provide quality health care services to all women and improve the health status of reproductive age group.

| MATERNAL HEALTH |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Logical Framework |  |  |  |  |  |  |  |  |  |
| Sl. | Goal | Sl. | Impact indicators |  |  |  |  |  |  |
| 1 | To provide quality health care services to all women and improve the health status of reproductive age group. . | 1.1 | Reducton in maternal mortality. |  |  |  |  |  |  |
| Sl. | Objectives | Sl. | Outcome indicators | Sl. | Strategy | Output indicators | Sl. | Activities | Process indicators |
| 2 | To increase Institutional delivery to 65% (current 60%) in year 2013-14. | 2.1 | Increase in Institutional Deliveries. | 2.1.1 | Increase safe institutional delivery (From 60% to 65 %). | No of Institutional deliveries | 2.1.1.1 | 1) Upgrading 15 SC to delivery points 2) SBA training of field workers 3)MCTS work plans to be strictly followed by ANM & ASHA. | 1) No. Of SC converted delivery points 2) No. of trained SBA 3) Work plans closely monitored by MOs and BPMU. |
|  |  |  |  | 2.1.2 | Upgrade 04 PHC/APHC to 24X7. | No Of PHC Upgraded | 2.1.2.1 | 1) Posting of Staff Nurses and ANM as per Delivery load. 2) Filling Medical Equipments gap through Seed Money 3) SBA training of Staff Nurses & ANM Posted. 4)Renovation of OT & Labour room using AMG. | 1) No. of Staff Nurses and ANM Posted. 2) Medical Equipments gap in PHC 3) No. of SBA trained Staff Nurses & ANM. 4) Renovation of OT & Labour room using AMG. |
|  |  |  |  | 2.1.3 | JSSK and KKS schemes will be Propogated | No of benificieries of JSSK & KKS Scheme | 2.1.2.3 | 1) Excessive campaign to propogate JSSK & KKS schemes ( phamplets, mass media Chaupals etc) 2) Scheme Benefits to be displayed at health institutions and also at Panchayat bhawans ( VHSC fund will be utilized). 3) ASHA/ ANM to ensure all benificieries to avail these schemes. | 1) Phampelets distributes, No of chaupals in which Schemes are adderessed. 2) no of banners displayed. 3) Achievement of ASHA / ANM |
| 3 | Increase the percentage of pregnant women receiving Complete ANC (47.4% AHS) and PNC(59% AHS) services. | 3.1 | Increase in early ANC & Complete ANC & PNC | 3.1.1 | Early ANC Reistration | No. Of ANC Registered in Ist Trimester | 3.1.1.1 | 1) Ensuring supply & use of Pregnancy detection Kit upto village level. 2) BCC regarding benefits of Early ANC throug ASHA, ANM, Mahila Mangal Dals, NGOs. 3)Use of MHV & MMU for both Service provider and IEC/ BCC. | 1) No. of Kits Utilized 2)BCC meetings held and through monthly reports of ASHA/ANM/ NGOs Etc 3) Monthly Reports of MHV &MMU |
|  |  |  |  | 3.1.2 | Increase coverage in ANC/PNC and ensure all complications receive timely attention. | No. of Mothers availing Complete ANC & PNC services | 3.1.2.1 | 1) Strengthening ASHA system with help of DARC. 2) Ensuring timely and correct payment to ASHA for PNC Packages. 3) MCTS will be used efficiently to track each pregnant women | 1) Achievement of ASHA. 2) Monitoring of payment gaps by DPMU MOIc BPMU at regular interval 3) Mother Tracked in MCTS |
| 4 | To Reduce the % anemic pregnant women from current 15% to 10%. | 4.1 | Decrease in %age of Anemic pregnant women. | 4.1.1 | To reduce anemia in pregnancy through distribution of IFA during 1st ANC Checkup. | No. of Mothers increasing hameoglobin level | 4.1.1.1 | 1 ) Timely Procurement of IFA tablets & disrbution upto sub center level. 2) BCC for increased use of locally available staple foods by pregnant women and lactating mothers. 3) Inter sectorial convergence with ICDS for nutrition for pregnant women | 1 ) Stock regsters. 2) No. of anemic pregnant mothers reported. |
|  |  |  |  | 4.1.2 | Detection of Anemic/Severe Anemic preganent mother | No. of Anemic mother detected | 4.1.2.1 | 1) Reorientation training of ANM to check Anemia of preganent mother. 2) Referal of preganent mother to DH/SDH. 3) IEC of High risk pregnant women regarding their place of delivery an to be escorted by ASHAs 4) Early Detection of anemic level of preganent mother by providind haemocheck scales to SC level. | 1) Training session held & mothers detected. 2)No of reffered cases 3) No. of Anemic mothers referred and assisted by ASHAs |

Activities:-

- Village Health And Nutrition Day

The objective is to increase early registration, improving occurrences of ANC/PNC checkups, promoting institutional deliveries, counselling on breast feeding and nutrition, family planning etc. leading to better maternal and child health. VHND is proposed to be organised once in a month at each Anganwadi Centre. ANMs Anganwadi Worker and ASHA will ensure their presence and will coordinate to make this activity at village level an effective intervention.

ANMs will be provided conveyance charges @ Rs. 100 per visit. An additional amount of Rs. 25 per camp is being made for covering the cost of tea etc. during the VHND. This payment would be done through the untied fund of VHSC. The formation of VHSC in the State is almost

Activities

- Counselling of expectant mothers on ANC, Identifying High risk pregnancy, Counselling on Safe  Delivery, Motivating for institutional delivery, PNC and Nutrition

- Counselling on Exclusive Breast feeding, Supplementary feeding, iodine deficiency and Child Immunization

- Distribution of IFA tablet

- Counselling of Family Planning methods and motivation and distribution of contraceptives.

- Identification and referral of mentally and physically challenged children

- Identifying and grading malnourished children for referral and further treatment.

- ANM will be visiting the AWC as per the schedule for which she will be getting Rs. 100 per Village Health and Nutrition Day for transportation.

- Aid the AWW in identifying mal-nourished children and referring to Higher health facility.

- Identification of mentally and physically challenged children and directing them accordingly.

- An amount of Rs. 25 per VHND will be available for meeting the expenses of Tea etc.

- Specific IEC materials will be developed to ensure their availability at the level of ANMs and ASHA for counselling and motivating clients at VHND.

- Awareness on Safe Drinking Water and Clean Environment.

Achievements In VHND

| Activities | 2010-11 | 2011-12 | 2012-13( OCT) |
| --- | --- | --- | --- |
| No. of VHNDs | 7265 | 6572 | 3639 (90%) |
| BCG | 3809 | 2709 | 1230 |
| DPT ( 3 dose) | 3373 | 3223 | 1647 |
| MEASLES | 3279 | 3634 | 1690 |
| POLIO ( 3 dose) | 3923 | 3223 | 1647 |
| ANC Registration | 4765 | 4579 | 2516 |
| TT | 5462 | 6044 | 2986 |
| 100 IFA | 6248 | 6692 | 4116 |
| COPPER T | 1861 | 1657 | 837 |
| Preg. Mother referral | 359 | 341 | 159 |
| No. of Grade III children | 56 | 236 | 173 |

Budget  at a glance for VHND:

| Activity | No | Unit Rate | Total |
| --- | --- | --- | --- |
| VHND’s | 6880 | 125 | 828000 |
| Grand Total |  |  | Rs 860000 |

The monitoring of VHND will be done by Village Health and Sanitation Committees. Generally VHND is carried out by ANM but as we have proposed 15 nos. of School Health Teams they will help in organizing VHND’s in places which are inaccessible for ANM’s and also in places where ANM’s are overburdened

- Janani Shishu Suraksha Yojana:

| Details of Pauri district |  |  |  |  |
| --- | --- | --- | --- | --- |
| Pop. (Lacs) |  | 6.86 |  |  |
| Expected Delivery |  |  | 13662 |  |
| DLHS-III |  | 29.4% |  |  |
| AHS 2011 |  | 53% |  |  |
| No. of Institutional Deliveries (HMIS) | 2005-06 |  |  | %age |
|  | 2006-07 | 2954 |  | 21 % |
|  | 2007-08 | 4429 |  | 31 % |
|  | 2008-09 | 6138 |  | 44 % |
|  | 2009-10 | 6990 |  | 52% |
|  | 2010-11 | 7292 |  | 53 % |
|  | 2011-12 | 7768 |  | 57 % |
|  | 2012-13 | 4798(Oct) |  | 60% |

Janani Shishu Surkasha Yojna ( Institutional vs Home ).

| S/No | Indicators | 2008-09 | 2009-10 | 2010-11 | 2011-12 | 2012-13 OCT |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Institutional Delivery | 44.8% | 52.15% | 53.04% | 56.85% | 60.20% |
| 2 | Home Delivery + Unreported Delivery | 55.2% | 41.85% | 46.96% | 43.15% | 39.80% |

According to HMIS & JSY data:

Budget of JSY at a Glance

| A | Janani Suraksha Yojana / JSY |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 1 | Home Deliveries | 400000 |  | 800 BPL ANC | Target of our Rural institutional deliverie being 7992 hence Rural BPL ANC will be 800 Aprox. ( 10%) |
| 2 | Institutional Deliveries | 0 |  |  | Target of our institutional deliverie for 2012-2013 is 8880 |
| 2.1 | Rural (90 %) | 15984000 |  | 7992 beneficiaries+ 7992 ASHA | 90 % of total target will be 7992 i.e 7992 Rural Deliveries |
| 2.2 | Urban (10 %) | 888000 |  | 888 beneficiaries | 10 % of total target will be 888 i.e 888 Urban Deliveries |
| 5 | Diet & Medicine | 2500000 |  | 7992 Rural Deliveries | Target of our institutional deliveries for 2012-2013 is 8880 |
| 6 | Other activities (JSY) | 1000000 |  | 5% administrative cost | Cost Of 04 HMIS fellow@5000 at DH & SDH and other Expenses |
|  | TOTAL | 20772000.00 |  |  |  |

c) TRAINING ON MATERNAL HEALTH

To increase institutional deliveries we first have to prepare ourselves in terms of

- Health Institutions

- Equipments

- Trained Manpower etc

In Financial year we are proposing some capacity building trainings for our delivery staff which are as below.

- SBA Training :

As we know have 02 SBA training Sites ( DH Pauri, SDH Kotdwara) we are planning 18 batches of SBA training for our District with 03 Participants in each batch.

Budget : 18 Batches X 70000 ( unit cost of 01 Batches) = Rs 1260000

- EmOC training : As we have shortage of Doctors in our District so we are planning to train 01 Lady Doctor ( Bironkhal CHC )

- MTP Training : 05 Doctors from 24 X 7 will be trained in MTP.

- RTI/ STI Training : 10 Doctors from 24 X 7 will be trained in RTI/ STI.

d) Maternal Death Audit

Background

Maternal death is a death of a woman during pregnancy, delivery and within 42 days of child- birth, irrespective of the site of pregnancy or the duration of pregnancy. Studies have revealed that 75% of the deaths are preventable and interventions to deal with maternal deaths can also reduce the infant deaths. A systematic fact finding mission is therefore required to analyze every maternal death. This is to determine the cause of maternal death which maybe a direct obstetric cause, indirect or a socioeconomic cause. This will assist in adopting corrective and preventive measures in the future. Hence there is a need to adopt a maternal death audit for early reporting, investigating and taking action in all the maternal deaths. Most of the maternal deaths can be averted even where resources are limited but, in order to do so, the right kind of information is needed in order to base actions. Knowing the statistics on the levels of maternal mortality is not enough - information is needed on the causes and

circumstances that have led to maternal deaths so as to initiate corrective measures to avert such deaths Moving in accordance with instruction and GO (which clearly defines the procedure of this Maternal Death Audit at the facility level.)  provided by State authorities we are still not able to get maternal audit reports from blocks.

Other Strategies:

- Involvement of Panchayat Members.

- Involvement of NGOs.

- Outreach Camps by Medical Officers at Sub-center HQ Villages.

- Safe Abortion Services.

- 24x7 Services required.

- Increasing Institutional Deliveries and Providing Basic Obstetric Care Services.

- Janani Suraksha Yojana.

- Quality Emergency Obstetric Care Services.

- Post-Natal care Services.

- Control of Anaemia among Women.

Activities:

- Involvement of Panchayat Members.

- Provide leadership to village, Gram Panchayat, Cluster & Block level teams

  - Training cell of UAHFWS will coordinate activities of this intervention that will be initiated in the coming year.

  - Training material to all the above programmes will be developed.

  - Training programmes will be conducted to all pradhans.

  - Panchayat may take appropriate action as pre-birth registration by motivating male partners/responsibility to VHSC & mahila Mangal Dals/ Pregnancy kit to be provided to Mahila Mangal Dal.

  - Reorganization of VHSC & their capacity building.

- Involvement of NGOs.

- Help District planning team to identify competent NGOs.

- Ensuring participation of NGOs/MNGOs in the Village Health & Sanitation Committee (VHSC) through official GOs.

- Use folk media/electronic media to increase awareness for JSY/Immunization/early signs of complicated pregnency & tackle superstitions, use NGO for this.

- Outreach Camps by Medical Officers at Sub-center HQ Villages.

- Medical officers of PHC with ANM and female supervisor will attend these camps to provide integrated services.

- Women should informed in advance the date and venue of camps

- There are 218 Sub centre in the district and 6 camps in each sub center will be conducted i.e. 1308 will be conducted in a year.

- Sub centre will be supplied with pregnancy diagnostic kits and adequate supply of IFA tablets will be ensured.

- Safe Abortion Services.

- Only Certified and Authorized person conduct MTPs.

- Implementation of PNDT act will be reviewed and all necessary measures will be initiated for its strict enforcement.

- All sites providing the MVA services for abortion will be publicized with proper display boards at each facility and IEC for the same will be conducted by IPC methods through ANMs, ASHAs and AWWs.

- 24x7 Services required.

  - Efforts to upgrade 5 CHCs for providing 24-hour delivery services will be made to provide round the clock services.

  - All health institutions will be equipped to provide 24 x 7 delivery services based on gaps identified with the help of facility survey conducted by the state.

  - Shortage of Staff nurses should be fulfilled for providing 24X7 services.

- Increasing Institutional Deliveries and Providing Basic Obstetric Care Services.

- IEC cell of UAHFWS will implement these activities and will identify suitable agencies for execution various IEC activities. Planning Cell of UAHFWS will coordinate the activities related to UP-gradation of CHC for 24x7 delivery services.

- Reimbursement procedures to Janani Suraksha Yojana will be reviewed and simplified to ensure prompt payment.

- Private transport owner’s network in remote areas of hill districts will be created for providing transport to pregnant women particularly during nights.

- Quality Emergency Obstetric Care Services.

- Planning, IEC and HR cells of UAHFWS will coordinate the activities related to this intervention.

- New born care corners will be created in the CHC/PHC.

- Publicity will be given to availability of emergency obstetric care services at CHCs with the help of hoardings, tinplates and laminated posters.

- The CHC will be linked to nearest blood banks.

- MOs will be trained in local anaesthesia techniques.

- Post-Natal care Services.

- Increasing awareness level among regarding post natal services with the help of district wide multimedia campaign.

- Training will be provided under composite training package.

- Involvement of Anganwadi workers, Dias and link workers and establishment of effective referral linkages.

- Control of Anaemia among Women.

- IEC cell in UAHFWS will select an advertising /communication agencies to develop messages on local best practices.

- The selected agency will undertake a review of local practices and locally grown iron-rich commodities in different region of district.

- Effective Antenatal care, Prophylactic iron and folic acid supplements, food security etc are some of the measures that would reduce these problem

- CHILD HEALTH

- The Child health status in the district is reasonably good. Immunization coverage in the district is reasonable good and 8 out of 10 children are full immunised. 4 out of 10 children are breast-fed within two hours of birth and 9 out of 10 children are breastfed for at least four months. Awareness of diarrhoea is reasonable good. 7 out of 10 Women are aware of danger signs of ARI/pneumonia.

- Indicators                                                                                Source: AHS 2011

| Indicator | Pauri | Uttarakhand |
| --- | --- | --- |
| Children received BCG (%) | 94.6 | 91.9 |
| Children received DPT (%) | 82.1 | 83.0 |
| Children received Measeals (%) | 87.6 | 82.6 |
| Children received full Immunization ( %) | 76.9 | 75.4 |
| Children received Vitamin A ( %) | 69.9 | 55.0 |
| Children received Polio Vaccine (3 dose) | 83.2 | 83.2 |
| Child feeding practices (Children under 3 years) |  |  |
| Children breastfed within one hour of birth (%) | 77.4 | 63.2 |
| Children breastfed within 24 hour of birth (%) | 96.4 | 86.1 DLHSIII |
| Children breastfed after 24 hour of birth (%) | 3.6 | 13.9 DLHSIII |

Situational Analysis:

Child Health Statistics:-

Source: HMIS Data source

| Activity | (06-07) | (07-08) | (08-09) | (09-10) | (10-11) | (11-12) | (12-13) Oct |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Full Immunization | 14930 | 14331 | 12948 | 13002 | 12822 | 11684 | 6360 (83%) |
| OPV3 Vaccine | 14847 | 14381 | 13877 | 13322 | 11842 | 10888 | 5322 (70%) |
| DPT3 | 14847 | 14381 | 13900 | 13322 | 11842 | 10888 | 5322 (70%) |
| BCG | 15102 | 14802 | 13465 | 12910 | 11142 | 12324 | 5989 (78%) |
| Measles Vaccine | 14930 | 14331 | 12948 | 13002 | 12822 | 11684 | 6360 (83%) |
| Vitamin A | 14219 | 3884 | 758 | 16789 | 16505 | 11817 | 8689 (82%) |

SWOT ANALYSIS CHILD HEALTH:

STRENGTH:

- Dropout rate from BCG(94.6%) to Measles (87.6%) is less( 7%).

- Sufficient and trained ANM (230) in Immunization.

- Regular supply of vaccines.

- Cold Chain maintenance is proper upto CHC/ PHC level.

- NRHM Vans also providing immunization services in 03 remote Blocks

- HMIS is fully functional while MCTS system is picking pace.

- DARC (945 Asha, 57 facilitator, 7 block coordinator). 7th Module trg  is completed in which focus is on HBNC which would be of great help to rural community.

WEAKNESS:

- Vacant post of Doctors/Pediatrician at PHCs/CHCs particular in rural area.

- Weak Neo Natal checkup in institution and also in home visits.

- Lack of nutrition counseling of family through health volunteers

- Non availability of transportation of Vaccine to Sub Center Level.

OPPURTUNITIES:

- High literacy rate among women.

- 96.4% child breastfeed within 24 hours.

- AWW, Mahilamangal dal, NGO’s.

THREATS:

- Low sex ratio 969 (0 to 6 year).

- Lack of knowledge of child care and poverty in rural area.

- Difficult geographical terrain.

- Communication problem.

- Gender Issues

- Natural disaster.

GOAL FOR CHILD HEALTH

To provide quality health care services and improve the health status of all children..

| CHILD HEALTH |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Logical Framework |  |  |  |  |  |  |  |  |  |
| Sl. | Goal | Sl. | Impact indicators |  |  |  |  |  |  |
| 1 | To provide quality health care services and improve the health status of all children. | 1.1 | To decrease IMR/ Infant Mortality |  |  |  |  |  |  |
| Sl. | Objectives | Sl. | Outcome indicators | Sl. | Strategy | Output indicators | Sl. | Activities | Process indicators |
| 2 | Reduction in Infant mortality from 43/1000 to 40/1000 in year 2013-14. | 2.1 | Reduction in IMR | 2.1.1 | Increase safe institutional delivery (From 60% to 65 %). | No of increased Inst. Deliveries | 2.1.1.1 | 1) Upgrade 04 PHC/APHC to 24X7. 2) Upgrade 15 Sub Centers into delivery points 3) SBA training of field workers 4)MCTS work plans to be strictly followed by ANM & ASHA. | 1) No of 24X7 In District 2) No. Of SC converted to delivery points. 3) No. of trained SBA 4) Work plans closely monitored by MOs and BPMU. |
|  |  |  |  | 2.1.2 | Increase coverage in complete ANC (47% to 70%), PNC (59% to 90%). | %age increase in ANC PNC coverage | 2.1.2.1 | 1) Strengthening ASHA system with help of DARC. 2) Ensuring timely and correct of ASHA for Immunization Packages. | 1) No. of ASHA assisting complete ANC, PNC 2) Payment done |
|  |  |  |  | 2.1.3 | To decrease neonatal death rate | No of Neonatal Deaths | 2.1.3.1 | 1) Strengthening of Mother Child Care Center at Medical College & NBSU at SDH Kotdwara. 2)Stergthining Existing NBCC ( 14 NBCC) 3)Setting up 10 New NBCC at Delivery Points. | 1) No of SNCU Established 2)no of functional NBCC. |
| 3 | Coverage of complete immunization of children in 12-23 months from 76.9% (AHS 2011) to 85% by 2013-14 | 3.1 | %age increase in children fully immunized | 3.1.1 | Compulsory 48 hours stay after delivery (At least 40 % of total deliveries at each institute) | No of Mothers staying 48 hrs | 3.1.1.1 | 1) 48 hrs stay to be displayed in Citizen charter.(JSSK & KKS). 2) Complication (in case of early exit) will be displayed. 3) Counseling of attendants for 48 hrs stay. | 1) Citizen charter 2) Displayed Boards in Institutions. 3) No. of 48 hrs stay |
|  |  |  |  | 3.1.2 | Immunization coverage to be looked after in Home deliveries | No of Home delivered Children immunized | 3.1.2.2 | 1) Proper follow up of home delivieries for both PNC and Immunization. 2) Awareness programme of population through PRI members | 1) Number of immunization done for Home deliviries. 2) Training schedule and progress of trainings of PRI members. |
| 4 | To reduce the % of low birth weight, underweight & anemic children. | 4.1 | %age of Children ( Under weight) anemic) | 4.1.1 | To reduce no of malnourished children | No. of malnourished childrens | 4.1.1.1 | Setting Up NRC (5 bedded) at DH Pauri | .Functioning of NRC |
|  |  |  |  | 4.1.2 | To enhance child health service through VHND. |  | 4.1.2.1 | 1) Use of school health team to visit VHNDS (Pauri is having 03 SH teams). 2) Community mobilizer of SH team to Mobilize children as well as parents for Healthy Practices | 1) Monthly Reports of SHT 2) Monthly Reports of SHT |
|  |  |  |  |  | Convergence with ICDS to maintain quality in child health services |  |  | 1) District as well as field level workers meetings would be organized and situation analysis would be done together. 2) | 1) No of meeting held with ICDS |

- Strategies/Activities planned for 2013-14:

- Integrated Management of Neo—Natal & Childhood Illnesses.

- In Financial Year 2013-14 we have proposed running cost of 1 Mother child care unit at Medical college sringar and  01 No of NBSU’s at Kotdwar.

- New Born Corner: As we are planning to devlop 15 SC’s into delivery points and also 4 PHC 24x7 into delivery points hence 19 units of baby warmer will be required in FY 2013-14.

| New born corner all 24x7 PHCs / Sub Center | 1000000 | Baby Warmer cost (Rs 50000) for 20 units ( 15 SC + 04 PHC +01 Spare) |
| --- | --- | --- |

- NRC (Nutritional Rehabilitation Centre)- A 5 bedded NRC is planned to be opened at DH Pauri in FY 2013-14

Objectives of NRC:

- To provide institutional care for children with acute malnutrition;

- To promote physical, mental and social growth of children with acute malnutrition;

- To build capacity of primary care givers in the home based management of malnourished children;

The admission criteria for the NRC will be as per the GoI guidelines and will be as following:

- Severe wasting and/or bipedal edema

- Moderately severe cases with complications (recurrent ARI and RD)

- <1 yr of age with lactation failure or mother expires

- Children with associated problems can only be admitted after stabilization at PHC/CHC/SDH/DH for recommended period decided by treating Physician

Monitoring & Evaluation of NRCs-

As conceptualised, and in accordance to the health related needs of ICDS, this concept of NRCs is proposed by the state to foster the improved convergence with ICDS and to address the health and nutrition related issues among severely malnourished children. Therefore, a joint monitoring committee will be formed at the district level to monitor and evaluate the NRC and its functioning. The details of the district level monitoring committees are mentioned in the following table:

| S. No. | Details and Desig. of the Officers | Associated as |
| --- | --- | --- |
| 1 | Chief Medical Officer | President |
| 2 | District Program Officer | Vice President |
| 3 | Dy. Chief Medical Officer (NRHM) | Member Secretary |
| 4 | CMS/MS of the hospital where NRC is established | Member |
| 5 | Child Development and Project Officers (All Blocks) | Member |
| 6 | District Program Manager (NRHM) | Member |
| 7 | Hospital Manager (Where NRC is located) | Member |
| 8 | Paediatrician of NRC | Member |
| 9 | Nutritionist cum Counsellor of NRC | Member |

Human Resource & Trainings under NRC

| S. No. | Name of the Position | Sanctioned Strength | Remuneration | Months | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | Superintendent (Dy CMO) | 1 | Nil | 12 | 0 |
| 2 | Project Coordinator (DPM/HM) | 1 | Nil | 12 | 0 |
| 3 | Nutritionist cum Counsellor | 1 | 10000 | 12 | 120000.00 |
| 4 | Medical Officer (Part-time) | 1 | 3000 | 12 | 36000.00 |
| 5 | Health Worker (Female) | 6 | 10000.00 | 12 | 720000.00 |
| 6 | Cook | 1 | 6000 | 12 | 72000 |
| Total Budget for Nutritional Rehabilitation Centre |  |  |  | 12 months | 948000.00 |

| S. No. | Budget Heads | Budget |
| --- | --- | --- |
| 1 | Non-recurring Cost |  |
| 1.1 | Civil Work | 500000.00 |
| 1.2 | Equipments, Instrument and Furniture | 200000.00 |
| 1.3 | Kitchen Supplies Starters and Catch up diet for children @ Rs. 15000/month | 180000.00 |
| 1.4 | Pharmacy supplies and Consumables | 180000.00 |
| 1.5 | Office Expenses | 40000.00 |

Hence, Total Budget for  NRC at DH Pauri  = Rs 2048000.00

- Weight Monitoring Campaign – We have proposed two Weight Monitoring Camps with ICDS department in FY 2012-13 .

- Budget-

| 2 special drives for low birth babies in campaign mode will be organized in 2013-14 | 603000 | Cost of 230 weighing machine (Rs 115000.00) + ASHA incentive @ Rs 200 per camp ( Rs 378000.00) + Stationary ( Rs 50000.00) + ASHA incentive for detecting low Birth weight babies @ Rs 100 per case ( Rs 60000.00) |
| --- | --- | --- |

- In addition to above proposed activity we would:

- Training programs will be organized at the District-level for the trainers.

- Doctors and ICDS functionaries who attended the district-level training will be the lead trainers for training of ANMs and AWWs and ASHAs.

- ASHA workers during their routine interaction with the ANMs in the district will be oriented towards dealing with child health issues and IPC will be reinforced with the help of ANMs and AWWs.

- Joint monitoring plan will be developed at the block level and implementation of IMNCI will be jointly monitored during monthly meetings by health department and ICDS.

- ORS will be supplied to ANMs and ASHAs for countering diarrhoea (dehydration).

School Health Programme:-

We started School Health Programme in August 2010 with 01 Team (01 MO male, 01 Mo female, 01 Community mobilizer & 01 Pharmacist) which was later increased to 04 Teams in financial year 2012-13. As per instruction of GOI as in Financial year 2013-14 Inter Colleges (272 Schools) have to be covered so we have proposed 01 SHT for each block so that each school can be covered at least 04 times in a year.

Activities -

- Medical examination of children will include detection of anaemia, Vitamin A deficiency, eye diseases, skin diseases, iodine deficiency disorders, worm infestations, dental diseases, respiratory diseases, emphasis on personal hygiene and other health related issues.

- For each student a health card will be maintained. For this education department will also be consulted.

- Complicated and difficult cases will be referred to the nearest health centre.

- Health Education should be included in Scholl Health Programme.

- ANM should attend the Parents teachers meeting in school and Provide health education.

- Preparation of School Health Programme Manual.

- Identify the Children who are suffering from major surgical disease and referred to higher facility through SHP.

- Budget :

| S.No | Head | unit cost | Total Cost for 12 Months |
| --- | --- | --- | --- |
| 1 | 30 MO/FMO Salary | @25000.00 | 9000000.00 |
| 2 | 15 Pharamcist | @15000.00 | 2700000.00 |
| 3 | 15 Optimical Asistant | @10000.00 | 1800000.00 |
| 4 | 1 Coordinator | @15000.00 | 180000.00 |
| 5 | 1 Regional Coordinator | @20000.00 | 240000.00 |
| 6 | 15 Vehicle | @40000.00 | 7200000.00 |
| 7 | DA | @300 /@200 | 500000.00 |
| 8 | Stationary | @200000 | 1000000.00 |
| 9 | Detailed School Health Plan Meeting | @4000 | 48000.00 |
| 10 | Medicine | @2000000 | 2000000.00 |
| 11 | Referred Children Surgery |  | 2000000.00 |
|  | Total |  | 26668000.00 |

| Total School Health Programme Cost | 26668000.00 | 15 Teams will be able to cover 2400 school in District Pauri on Quaterly Basis. | Salary and Running Cost of 15 SHP Team + 01 District coordinator cost & 01 Regional coordinator cost |
| --- | --- | --- | --- |

Activities:

- Complete Immunization of Children.

- Special efforts will be made to identify children not immunized at all. Community support will be sought and link person services will be utilized to mobilize such children.

- Provide logistic support to vaccine transportation

- Warehousing & Manpower support for vaccine store.

- Motivating villagers especially mothers to bring their children to the identified centres.

- Regular monitoring & reporting system for ILR, deep fridge temperature as per guidelines.

- Monitoring systems will be strengthened to drastically reduce drop out rates.

- Cold chain systems will be streamlined from district to PHC level.

- Improving Early and Exclusive Feeding Practices.

- Select a reputed communication agency for the Communication campaign, designed to address myths associated with breastfeeding and to improve awareness about advantages of breastfeeding without squeezing milk and exclusive breastfeeding for 6 months.

- A one-day orientation programmes on the importance of counselling mothers about breastfeeding will be conducted for all medical officers.

- ASHA will be counselling the pregnant females and her family on issues of early breastfeeding and post partum contraception.

- Relevant IEC material will be disseminated to all the participants and all health institutions.

- Incentive to ASHA for Promoting the mother for Breast Feeding and Referred Sick Born.

- Diarrhoeal/Jaundice control activities.

- VHSC should form testing water testing committee in every village/Panachayat should involved in water testing.

- BCC plan to inculcate safe drinking habits in the villages through NGOs.

- Panchayat should ensure 100% toilets in each village under TSC scheme.

- Special focus on underprivileged and socio-economically disadvantaged groups.

- Each Panchayat should have water testing kit and training/system regular reporting be eveloved/directly monitored by District NRHM mission through DPMU to ensure appropriate action.

- Double tank system for filtration should be made available in each village.

- Team approach with department of Women and Child Welfare.

- Relevant IEC material will be disseminated to all the participants and all health institutions.

- Vitamin. A supplementation & Deforming

- BCC for improving attendance at AWWs for supplementary feeding

- Growth chart monitoring.

3.Fertility and Family Planning:

- The total fertility rate in Pauri garhwal is 2.4 AHS 2011 Knowledge of modern family planning methods was high eligible women and 52.7% were Currently modern method of contraception. Use of spacing methods was negligible and condom was the most poplar spacing method. Parity at acceptance of Modern family planning method was twice higher for women with three or more children in comparison to those who had two children. Use of family planning Methods increased with the number of surviving sons.

- Situational Analysis

Family Planning:-

| Activity | AHS 2011 |
| --- | --- |
| Condom Users | 10.7 |
| OP Users | 3.0 |
| IUD insertion | 1.2 |
| Female Sterilization | 36.2 |
| Male Sterilization | 1.2 |
| Any Other Method | 11.9 |

| Activity | (04-05) % | (05-06) % | (06-07) % | (07-08) % | (08-09) % | (09-10) % | (10-11) % | (11-12) % | (12-13) Oct % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Condom Users | 83.67 | 79.22 | 90.76 | 76.93 | 90.54 | 72.0 | 50.0 | 59.6 | 32.67 |
| OP Users | 92.87 | 88.96 | 103.41 | 100.9 | 108.9 | 105.5 | 63.5 | 85.9 | 28.73 |
| IUD insertion | 82.58 | 80.97 | 70.20 | 98.3 | 95.56 | 89.0 | 85.50 | 80.99 | 39.85 |
| Sterilization | 104.55 | 92.04 | 73.65 | 106.18 | 94.06 | 90.66 | 91.2 | 84.7 | 16.03 |

Percentage of Family Planning Methods used in 2011-12.

Sterilization:

| Sterilization | 2004-05 | 2005-06 | 2006-07 | 2007-08 | 2008-09 | 2009-10 | 2010-11 | 2011-12 | 2012-13 Oct |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Male | 100 | 115 | 84 | 127 | 183 | 296 | 197 | 193 | 33 |
| Female | 2910 | 2719 | 2569 | 2846 | 3002 | 2774 | 2540 | 2433 | 464 |

SWOT ANALYSIS FAMILY PLANNING:

STRENGTH:

- Sufficient Field staff

- Regular supply of Contraceptive.

- Well equipped Infrastructure for providing FP services.

- NRHM Vans also Supply Contraceptive for Spacing Method in 03 remote Blocks

- Good No of VHND to Supply Contraceptive for Spacing and counseling for Permanent method.

- DARC (945 Asha trained in HBNC, 57 facilitator, 7 block coordinator)

WEAKNESS:

- Vacant post of Trained Doctors at PHCs/CHCs particular in rural area.

- 06 Doc trained in NSV but only 02 performing.

- Poor follow up of Spacing method.

- Re orientation needed for field staff.

- Number of failure cases ( 90 in last 04 years)

OPPURTUNITIES:

- High literacy rate 77% census 2011.

- Male population large (only 0.3% male sterl. Are done).

- High marriage age (96.8% marrying above legal age).

- 06 trained surgeon in minilap.

- AWW, Mahilamangal dal, NGO’s.

- Easy availability of Contraceptive etc in Market

THREATS:

- Poor participation by male community.

- Desire for Son.

- Late acceptance for permanent method.

- Lack of Awareness in rural area.

- Difficult geographical terrain.

- Myths

- Natural disaster.

GOAL FOR FAMILY PLANNING

To provide quality family planning services to achieve population stabilization.

| Family Planning |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Logical Framework |  |  |  |  |  |  |  |  |  |
| Sl. | Goal | Sl. | Impact indicators |  |  |  |  |  |  |
| 1 | To provide quality family planning services to achieve population stabilization. | 1.1 | To decrease TFR To increase sex ratio |  |  |  |  |  |  |
| Sl. | Objectives | Sl. | Outcome indicators | Sl. | Strategy | Output indicators | Sl. | Activities | Process Indicator |
| 2 | Reduce Birth rate from 19.9 to 18 in year 2013-14. | 2.1 | Reduction in birth Rate | 2.1.1 | Training of existing Doctor . | No. of Doctors providing family planning services | 2.1.1.1 | a) Training of 04 Male Doc for NSV. b) Training of 01 female Doc for Minilap. c)Reorientation of 04 non performing NSV trained doctors. d)O6 trained minilap surgeon at Medical college will be used to provide FP services at peripheries. | 1) No. of Male Doc trained in NSV. 2)No. of Minilap trained Doc 3).No of reoriented Doc. 4)Cases done by Minilap Surgeon. |
|  |  |  |  | 2.1.2 | Private practionors would be used for FP services at kotdwara ( 2 Priv. Surgeon available). | No. of Private practitioner providing family planning services | 2.1.2.2 | Accreditation/ MoU with 02 private practicinors in Kotdwtara for providing sterlization services . | No of sterilization cases done. |
|  |  |  |  | 2.1.3 | Improving Drop back facilities at FP camps (All cases will be drop backed) | Benificieries utilizing Drop Back Facilities | 2.1.3.3 | 1) More fund will be demanded in DHAP for providing Drop Back services for beneficiaries. 2) Tie up with private vehciles providers. | 1) Approval of funds demanded. 2)No of beneficieries droped. |
| 3 | To convert Non users from 42% to 35% by 2013-14 | 3.1 | %age of Non users after 2013-14 | 3.1.1 | To increase IUCD Prevalence rate from 1.3% to 2%. | %age increase in IUCD Users. | 3.1.1.1 | 1) Every ANM would be provided with kits & would be traind for IUCD services 2)Reorientation for ANM and setting ELA for ANM for IUCD insertion. 3) Incentivising motivator for IUCD Insertion. | 1)No. of ANM having IUCD Kits 2)No. of ANM reoriented & Monthly report of ANM 3)Incentives for IUCD availed. |
|  |  |  |  | 3.1.2 | To increase Male participation in sterlization from 0.3% to 1%. | %age increase in Male Sterlization. | 3.1.2.2 | 1) Organizing 10 NSV Camps in year 2013-14. 2) Involving and rewarding SSS for motivating Male sterl.. 3)Planning for Fixed Date, Fixed Place approch at selected institution for providing NSV Services | 1) Number of NSV Camps organized in year 2013-14. 2) Male sterl.. Motivated by SSS. 3) No. of cases done in such dates. |
|  |  |  |  | 3.1.3 | To increase spacing Methord especially Pills ( from 3.0% to 5%) and Condoms ( from 10.7% to 15 %) | %age increase in Pills & condom users | 3.1.3.1 | 1) Ensuring regular & timely supply of Pills and Condoms upto SC level. 2) Awarness of women & supply of Pills through ASHA/ANM. 3) Awarness of Men & supply of condoms through SSS.4) Follow up of clients by ANM/ASHA/SSS. | 1) Stock out details upto SC level . 2) ASHA diaries & ANM monthly reports. 3)SSS Diaries . 4)Reports of pregnancy of clients using Pills & Condoms. |
| 4 | Reduce couples unmet needs from 19.6% to 15%. | 4.1 | % decrease in the unmet needs | 4.1.1 | Organizing Family Planning Camps ( 45 camps in year 2013-14) | Qualitative achivement of Family Planning Camps camps | 4.1.1.1 | 45 Family Planning Camps camps will be organized with help of 03 Teams and these camps will be monitered both quantitatively and Qualitatively by MOs and other officials | No. of camps organied |
|  |  |  |  |  | Pick up and drop back facility for beneficiary from remote areas | Benificieries utilizing Drop Back Facilities | 4.1.1.2 | Budget will be proposed in DHAP and by tie ups with local vehicle provider | Approval of Budget and no of benifieceries droped |
|  |  |  |  |  | Ensuring regular supply of Contraceptives. | Proper Supply of Contraceptives etc. | 4.1.1.3 | Advance Planning of NSV anr RCH camps so that no stock out happens. 2) Proper maintenance of Stock register and timely procurement | No. of Stock outs |

Activites:

a)Family Planning Camps :

Pauri Garhwal is a hilly district, with many problems in connectivity, and it is often difficult for needy persons to come to health institutions for availing Sterilization services. The shortage of service providers aggravates the problem of inaccessibility. In order to counter these constraints, the frequency of  Sterilization camps fixed for our district is 03 camps per blocks which work out to 45 camps in financial year 2013-14 (03 camps X 15 Blocks). In addition to Sterilization camps 03 nos of population weeks will be conducted in our District. The dates of population weeks will be decided later after due consultation with Medical staff, local population etc and issues like availability of beneficiaries , medical team, weather condition and also local constraints would be logically dealt

In Financial year 2013-14 an additional Budget of 06 Lakhs has been demanded for organization of Population Weeks (03 Nos).

Budget –

| Family Planning camps @ 7500/- & Population Forthnite | 937500 | 45 camps will be held in 15 blocks and 03 population weeks will be held in next financial year ( 45 X 7500 + 600000 for Population Week) | Taret 3100 Sterlization |
| --- | --- | --- | --- |
| (3 camps per block per year 02 female camps & 01 male camps) |  |  | Target for population week 350X3=1050 Taret for Family Planning camp 45X30 = 1350 |

Supplementary Activities:

- Increasing the demand for Family Planning Services.

- BCC campaign covering all the rural and urban areas.

- VHND will be utilised to put across the views and counsel the targeted couples through interpersonal communication.

- Folk-media has been an effective tool and efforts will be made to utilize their skills to increase awareness on family planning especially on male participation, particularly for the villages of Hill districts

- Assessment of the satisfaction level of clients through ASHA will be attempted from this year onwards.

- Display of IEC material at service sites describing the range of available services.

- Clinic Based IUCD Insertion Training for ANMs.

- Training cell of UAHFWS will execute this intervention.

- Sites will be selected depending on the availability of lady medical officer and staff nurse for IUCD insertion training. Each team will provide one week training to ANMs .

- All trained ANMS/LHV will be provided with manuals, poster instructions for IUCD insertion and IUCD insertion kit.

- Monitoring the performance of ANMs/LHV with the help of checklist provided to them.

- Clinical Training for Female and Male Sterilization Services.

- Laparoscopy trainings will be organized to provide trainings to Medical Officers/Staff Nurses and OT.

- Minilap Trainings will also be conducted to train batches comprising of Medical Officers/Staff Nurses and OT.

- IUD training for newly recruited ANMs in 218 Sub Centers.

- Emergency Contraception.

- Training cell of UAHFWS in all collaboration with the Logistics cell will coordinate these activities.

- IEC material on emergency contraception will be collected, collated and printed.

- Training of medical officer about emergency contraceptives and their use.

- Maintaining the availability of emergency contraceptives at PHC/CHC level.

- Supplying emergency contraceptives will also be streamlined.

- Use of services of Mobile Health van.

- Use of services of Mobile Health van in un served areas.

- Taking services of Private Providers.

- Using services of private Providers for providing sterilization.

- Training doctors in conducting ‘No Scalpel Vasectomy’ surgeries.

- At least one medical officer trained in each FRU conducting NSV.

- Special Training camps should be organized at State level.

4.	ADOLESCENT REPRODUCTIVE AND SEXUAL HEALTH (ARSH)

One of the technical strategies adopted to achieve the goals of reducing IMR, MMR and TFR in the State was to enhance focus on Adolescent Health. Comprising of more than 20% of the Population this section of the society remained largely unattended in the sense that no intervention under NRHM was planned till almost 2009-10 .

In financial year 2012-2013 we had proposed 02 block Bironkhal & Dugadda  because both the blocks are big and the population of young age group is more. In this year we have started ARSH programme in these blocks  by the help of ASHA Resource center (NGO).  For Financial year 2013-14 we have proposed Two more block Thalisain & Nainidanda because the Literacy and sex Ratio are less and also the block is undeveloped.

Budget :

| ARSH | 4000000.00 | Running Cost for 04 Blocks ( Bironkhal Dugadda Thalisain & Nainidanda ) |
| --- | --- | --- |

Strategies:

- Teachers and peer educators enabled to provide information to adolescents..

- Adolescent’s friendly services.

- Depot holders knowledgeable on transmission and prevention of STIs/HIV/AIDS and dual protection.

- Quality RTI/STI case management services accessible.

- Women and community mobilized against and supported to address gender issues.

- Organizations Like NGOs/ MNGOs/shelter home, police machinery and other similar institutions enabled to address gender issues.

Activities:

- Teachers and peer educators enabled to provide information to adolescents.

- Training & reorientation of teachers.

- Orientation of peer educators.

- Organizing PHC level events and campaigns by adolescents.

- Health Checkups by Medical Officers at AnganWadi Centers will be organized periodically

- Adolescent’s friendly services.

- Iron and calcium supplementation to girls in selected pockets.

- Anthalmentic supplementation in selected pockets.

- Special emphasis on preventions and management of malaria.

- Screening for sickle cell anaemia

- Adolescent's friendly service clinics including counselling services on fixed days at selected institutes

- Organizing adolescents melas at PHC level

- Organizing health check ups and information camps for adolescents.

- Organizing Innovative activities for improving access to information and services.

- Depot holders knowledgeable on transmission and prevention of STIs/HIV/AIDS and dual protection.

- Village level Depot holder establishment.

- Orientation of village level depot holders.

- Quality RTI/STI case management services accessible.

- Training of MOS and Lab. Technicians clinical management approach.

- Orientation of health staff for screening and referral clients and for transacting messages on prevention and management of RTIs/STIs/safe sex.

- Provision of equipment and laboratory agents.

- Organizing monthly/quarterly camps at fixed venues, where regular services are not available.

- Women and community mobilized against and supported to address gender issues.

- Sensitization of health functionaries, PRI member, NGOs and others on issues related to gender issues.

- Sensitization workshop for Zila, block and village Panchyat members on gender issues.

- Organization of events and campaigns.

- Organizations Like NGOs/ MNGOs/shelter home, police machinery and other similar institutions enabled to address gender issues.

- NGO supported for functioning of legal aid and counselling for women victims of violence.

- Sensitization workshop for block level inter-sectoral government functionaries on gender issues, identification and referrals, followed by annual review workshops.

- Outreach activities of counselling centre.

5 	URBAN HEALTH PROJECT

Urban Health Project has been implemented in our State since 2009. in year 2009-10 Haridwar & Haldwani were selected and in year 2010-11  two another cities Dehradun and Roorkee were added to this Project. In financial year 2012-13 we had proposed Two (02) Urban Health Posts for Kotdwara, Which is sanctioned by the center government.

The process of opening Two Urban Health Post in kotdwara slum area is started in October month. In Financial year 2013-14 We are going to strengthen these two new  Urban Health Post

Activities Proposed:

- Development of urban health plan and GIS Mapping of slums and health facilities in Kotdwara.

  - Conduct situation analysis and stakeholders consultations to understand the availability of  first tier health facilities, reach of services to the urban poor, private health facilities accessed by the urban poor, human resources adequacy at the public first tier facilities, presence of community based institutions and their existing linkages with service providers etc.

  - Conduct listing of all slums including identification of additional slums/poverty clusters

  - Conduct stakeholders meetings to verify the findings related to slums and health facilities

  - Conduct GIS mapping of Govt .health facilities and  slums

  - Identification of potential NGOs for implementing urban health activities in the city

  - Preparation of urban health plan detailing the number of additional first tier facilities required, man power requirement, catchment area per urban health centre including the unlisted slums/additional slums/poverty clusters, potential NGO partners and their possible role, referral mechanism, community based institutions and their proposed role, improving linkages between slum communities and service providers, plan for outreach sessions, inter sectoral  coordination mechanism at different levels, review and monitoring plan etc.

- Development of urban slum health program related guidelines for a) identification/selection of USHA,  b)formation and mentoring of Mahila Arogya Samitis in slums, c)promotion of inter-sectoral coordination committee/forum at UHC level, d) constitution of  City level inter-sectoral Urban Health Task Force/Committees

- Recruitment and training of ASHA/USHA: The community volunteers/ASHA/USHA would be functional as per NRHM norms and would be receiving performance based incentives like rural ASHAs. ASHA/USHA kit would also be provided under NRHM as per norms. Training will factor urban slum specific issues.

- Development of BCC strategy for slum population and roll out in three cities:

Group discussions with mothers, other community members in slums will be conducted in these cities to understand the prevailing practices, barriers to appropriate practices, and community perceptions. The findings would contribute to development of BCC approaches. The various channels like Interpersonal Communication (IPC), mothers’ meetings, Street plays, Mass media such as use of local cable TV, peer group communication would be used as appropriate based on needs assessment.

The BCC strategy would focus on:

- Use of various media as relevant to the area/city.

- Reach to each and every beneficiary

- Capacity building of service provider as well as NGO functionaries, community representatives/ communities

- Other activities: Some event and activities would be conducted to celebrate national and international days/weeks to aware the communities such as:

  - Healthy baby competition during World Breastfeeding Week

  - Awareness/competition during National Nutrition Week etc.

- Training and capacity building:

Organize training sessions/workshops/study tours/ for State Officials, State and City Program Management Units staff and field functionaries

- Program Review, Monitoring and Evaluation:

- Conduct baseline survey in Roorkee and Dehradun

- Develop program monitoring indicators and use them for review

- Program implementation activities will be monitored and reviewed through:

    - Regular city urban health task force meetings

    - Field visits by city and state PMU staff

    - Program review by CMO under NRHM

    - Monthly progress reports and documentation

Budget :

| Urban RCH Services | 4295100 | Running cost of 02 Urban Health Post in Kotdwara (Budget is in accordance with guidelines provided by State Officials) |
| --- | --- | --- |

6.	INNOVATIONS/NGOS/PPP

PCPNDT CAMPAIGN AT DISTRICT LEVEL

While the general sex ratio in our District is 1103/1000 males(census 2011)but sex ratio  within age group 0-6 years is 929/1000(census 2011)males which is alarming which if not controlled in time  can become a serious problem in coming time. While there could be other reasons for this situation, the most likely is the misuse of available diagnostic facilities and illegal abortions.

In District Pauri there are 15 Diagnostic Machines and 01 Mobile Diagnostic machine out of these 05 are from Govt. Sector and rest are placed in Srinager & Kotdwara. All machines are registered and proper reporting is done by these units. In addition random check ups are being carried out by CMO & Dy CMO.

The PNDT Act prohibits sex determination tests but its enforcement is not very effective in many places. Strict enforcement of the act involving all the enforcement agencies will have to be ensured so as to make this act a success.

In addition a more effective communication campaign at our district is proposed to be conducted with involvement of              judiciary to make service providers and the general population aware of PNDT Act.

Apart from this, the district level PC & PNDT cells is operationalizing  in which on District Coordinator is recruited last year 2012-13. This coordinator will report to the District Nodal Officer through Dy. CMO (NRHM).

Activities

- Implementation of PNDT act will be reviewed and all necessary measures will be initiated for its strict enforcement.

- Action against illegal/ unregistered diagnostic facilities and clinics. For this sensitization of officials of enforcing agencies is proposed.

- IEC campaign will be conducted addressing both private and public health service providers and also general community on PNDT Act.

- Law enforcement agencies will be sensitized to facilitate its implementation in the true spirit.

- Prosecution of suspects and violators as per the provisions of the act.

- Regularly Collecting reports from ASHA’s regarding Village level Child Sex Ratios.

- Arrangements for confidentiality and rewards for whistle blowers.

- Tracking of Pregnancies, MTPs, Birth Registration and Child Sex Ratio.

Budget Part

| S.No | Head | Unit | Amount |
| --- | --- | --- | --- |
| 1 | District Coordinator Salary | 1 | 240000.00 |
| 2 | Travel by DC (PNDT) | 3,000.00 | 36000.00 |
| 3 | Office Maintenance Cost for PNDT Cells | 3000.00 | 36000.00 |
| 4 | Rewards for whistle blowers | 500.00 | 3000.00 |
|  |  |  | 315000 |

7. NRHM ADDITIONALITIES:

Focus of NRHM is to strengthen primary health care through grass root level public health interventions based on community ownership. The duration of NRHM is extended to Five years (2012-2017). It seeks to provide effective health care to the entire rural population in the country with special focus on High Focus states that have weak public health indicators.

- Accredited Social Health Activist (ASHA).

National Rural health Mission aims to provide health services to the vulnerable section of the rural area. Although there is a vast infrastructure of health personnel in rural area, there is a need to improve the reach of services to the un- reached areas.

Amongst a host of strategies adopted for the purpose of achieving the defined goals of NRHM launched in April 2005, one relates to the improvement in the access to health care at the household level through the mobilization efforts of ASHA.

ASHA is responsible for mobilizing and providing information to the community on the need for timely utilization of health and family welfare services, especially to the pregnant women. Empowered with knowledge and a drug-kit to deliver first-contact healthcare, every ASHA is expected be the catalyst for community participation in public health programmes in her village.

ASHAs involvement in various health activities as Motivator under NRHM:

- Early Registration

- 3 Check up (ANC)

- TT Immunization

- Identification of complicated cases of ANC and timely referral.

- Institutional Delivery (JSY)

- Early Breast Feeding i.e. within six hours and Exclusive Breast feeding

- PNC & HBNC Visits.

- Complete Immunization (Up to Measles)

- Motivator for hygiene and sanitation (e.g. completion of Toilet construction)

- DOTS programme

- Motivator for family planning

- Leprosy detection and complete treatment of PB case and MB case

- Social mobilisation of children

- Cataract operation in Govt. and private hospital

- Training in motivation for post partum and sterilization.

Status of ASHA in District Pauri  Block PHC Wise ASHAs Details:

| S. No | Block PHC/CHC | No of Gram Panchayats | Current Status | Trained up to 7th module | Trained in RSBY, ARSH, Homeopathy | HBNC 3 round |
| --- | --- | --- | --- | --- | --- | --- |
| 01 | Patisain | 83 | 69 | 62 | 65 | 69 |
| 02 | Pabau | 74 | 63 | 55 | 58 | 63 |
| 03 | Parsundakhal | 64 | 52 | 51 | 49 | 52 |
| 04 | Kot | 68 | 49 | 48 | 47 | 48 |
| 05 | Khirsu | 43 | 33 | 30 | 29 | 32 |
| 06 | Ghandiyal | 87 | 59 | 54 | 55 | 59 |
| 07 | Pokhra | 57 | 41 | 36 | 39 | 41 |
| 08 | Jaiharikhal | 74 | 41 | 39 | 36 | 42 |
| 09 | Rikhnikhal | 81 | 61 | 40 | 58 | 59 |
| 10 | Dugadda | 99 | 136 | 129 | 125 | 137 |
| 11 | Dadamandi | 99 | 58 | 47 | 52 | 56 |
| 12 | Yamkeshwar | 86 | 77 | 76 | 78 | 78 |
| 13 | Thalisain | 102 | 75 | 63 | 74 | 75 |
| 14 | Bironkhal | 102 | 64 | 53 | 59 | 60 |
| 15 | Nainidanda | 87 | 67 | 57 | 61 | 59 |
| Total |  | 1206 | 945 | 922 | 932 | 930 |

Activities in financial year 2013-14.

In district pauri garhwal there are 57 ASHA Facilators and 945 ASHA’s. All 57 ASHA Facilators will be  trained in financial year 2013-14 and also 945 ASHA’s will be provided with 7th & 8th module training.

Supplementry Activites:

- Selection of New Active ASHA in place of NON-Functional ASHA.

- To Locate Non-Functional ASHA.

- She will be a married woman resident of that village in the age group of 25 – 45 years.

- Selection of ASHA.from three selected names.

- The initial criteria were that she should be literate with education up to VIIIth standard.  .

- Anganwadi helper / part time attendant will be given preference while selecting the ASHA.

- Training of New Selected ASHA & left ASHA from 1 to 6th module.

- Compensation to ASHA.

All the ASHA will be will be compensated based on their performance as per the decision taken by the

Gramsabha.

- Giving presumptive treatment.

- For children fully protected.

- Pregnant women fully protected.

- Early & timely information to CHC/PHC about epidemic.

- Weighing newborns.

- Assist during conduct of delivery.

- Post natal visits.

- Eligible couples counselled & promoted for any contraceptive method or Family planning.

- Pregnant women taken to institution for delivery etc.

- Provision of DOTS.

- Untied fund kept at sub centre level may be used for paying compensation to them.

- Reporting outbreak if happened in her area.

Kits to ASHA.

- All ASHS’s have been provide with Drug kit & delivery kit ( Both Allopathic & Homeopathic).

- These kits are replenished timely .

- New selected ASHA’s will be given Drug kit & delivery kit after completion of training, which would be replenished at regular interval.

- She shall dispense the drugs at the local level at times of need.

Status of District ASHA Resource Centre (DARC):

In District  Pauri Garhwal DARC is being run by ASTHA SEWA SASTHAN . As per MoU signed between Health department & MNGO, DARC has been made responsible for assisting the health department in recruitment of ASHA workers, their capacity building and overall development in the district. DARC has also assisted in sorting out ASHA drop out cases in the year 2010-11.

Staff structure of DARC:

DARC Coordinator       = 1

Community Mobiliser   = 1

Data Entry Operator    = 1

Block Co-ordinator      =  07

Asha Facilitator          = 57

Budget :  Running cost for DARC at Pauri : Rs 4732800

B.	INFRASTRUCTURE AND RELATED MATTERS

B.1	Mobile Medical Units

The State of Uttarakhand is characterized by mountainous and geographically hostile terrain having sparse and scattered population. Communities living in the remote and disadvantaged areas, especially the BPL population and women are generally unable to access reliable and cost effective healthcare services. This is mainly due to the secondary costs associated with seeking healthcare services at block/district headquarter towns, such as cost of commuting, wage loss, etc.

The Government of Uttarakhand has taken several initiatives to improve access to healthcare services for the disadvantaged communities. One such initiative is to provide healthcare services through the ‘Mobile Health Clinic’ (MHC). The provision of these Mobile Health Clinics has increased the outreach of healthcare services to the hitherto underserved and un-served regions of the State. The concept of healthcare service delivery through Mobile Health Clinics has been implemented in these areas using three distinct MHC models –

In District Pauri Garhwal following MMU are operating:

      - Jain Video On Wheels :  Jain Video On Wheels is operating in our District and is responsible in organizing Health Camps in all 15  Blocks. There achievement is shown below:

Achievement in Year 2011-12

| S No. | Month | No of Camps | New Pts. | Old Pts. | Total OPD Pts. | No. of Referred Cases | No. ANC Cases | No. of USG |  | Xray |  | Path Invest. |  | E.C.G. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | A.P.L | B.P.L | A.P.L | B.P.L | A.P.L | B.P.L | A.P.L | B.P.L |
| 1 | April | 15 | 827 | 88 | 915 | 88 | 46 | 86 | 66 | 33 | 24 | 187 | 241 | 9 | 6 |
| 2 | May | 15 | 897 | 96 | 993 | 85 | 63 | 107 | 111 | 59 | 61 | 298 | 300 | 3 | 2 |
| 3 | June | 15 | 1058 | 95 | 1153 | 94 | 99 | 121 | 108 | 44 | 57 | 378 | 312 | 7 | 1 |
| 4 | July | 15 | 1187 | 103 | 1290 | 72 | 82 | 107 | 102 | 65 | 98 | 364 | 299 | 2 | 4 |
| 5 | August | 15 | 755 | 79 | 834 | 67 | 40 | 57 | 79 | 28 | 59 | 191 | 153 | 0 | 2 |
| 6 | September | 15 | 1209 | 98 | 1307 | 43 | 76 | 136 | 115 | 94 | 115 | 179 | 97 | 3 | 2 |
| 7 | October | 15 | 855 | 85 | 940 | 68 | 76 | 113 | 98 | 54 | 100 | 382 | 325 | 7 | 3 |
| 8 | November | 15 | 878 | 70 | 948 | 91 | 59 | 0 | 0 | 67 | 118 | 393 | 222 | 8 | 7 |
| 9 | December | 15 | 992 | 93 | 1085 | 93 | 90 | 159 | 131 | 7 | 11 | 447 | 326 | 14 | 4 |
| 10 | January | 15 | 680 | 103 | 783 | 67 | 71 | 104 | 60 | 52 | 51 | 401 | 251 | 5 | 6 |
| 11 | February | 15 | 1060 | 88 | 1148 | 115 | 102 | 157 | 97 | 59 | 100 | 601 | 243 | 16 | 7 |
| 12 | March | 15 | 1107 | 86 | 1193 | 112 | 76 | 157 | 101 | 39 | 139 | 549 | 341 | 6 | 3 |
|  | Total |  | 11505 | 1084 | 12589 | 995 | 880 | 1304 | 1068 | 601 | 933 | 4370 | 3110 | 80 | 47 |

2) Rajbhara:  Rajbhara medicare pvt ltd also running 01 mobile van from July 2011 which has been given responsibility of organizing camps in 03 Blocks ( Bironkhal, Nainidanda & Thalisain) There achievement is shown below:

Achievement in Year 2011-12

| Month | No of Health Camp | Camp Location | New Pts. | Old Pts. | Total OPD Pts. | No. of Referred Cases | No. ANC Cases | Number of clients counseled for FP | Number of clients received Oral Pills | Number of clients received Condoms no.packs | counseling for breast feeding | Path Invest. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| April 2011 to March 2012 | 190 | 3 Blocks Bironkhal, Nainidanda & Thalisain | 5829 | 263 | 6092 | 357 | 35 | 1011 | 71 | 2181 | 644 | 825 |

Budget proposed

  - NRHM MMU  =Rs 2300000  This 23 lakhs includes Rs 50000 for paying incentive   to ASHA(@Rs per session) and Rs 1.5 Lakhs  for repair and maintenance of vehicles according to state rules

B.2	Emergency and Referral Services

The biggest hurdle in Uttarakhand is geographical access. It is important that the beneficiary reaches the institutions for institutional deliveries especially in difficult to reach areas. State addressed this issue by collaborating with EMRI services. 108 ambulances have solved this problem to a large extent as these are located in each block.

EMRI 108 van is providing referral transport to each call made to them through toll free services. A spurt was noticed in the number of women seeking delivery services using the emergency transportation services, EMRI 108, begun by the state in May 2008. As per the data available against the total emergencies handled by EMRI pregnancy related cases amount to 41% which has significantly contributed to increase in the number of institutional deliveries in the State.

GVK EMRI Uttarakhand is currently running 16 ambulances in District pauri Garhwal.

8.  HUMAN RESOURCES RELATED MATTERS

1 Contractual ANM’s/Staff Nurse :   In District Pauri Garhwal presently 20 Contractual ANM’s &

13 Staff nurses are Working.

Required:   ANM  =   32 New ( for 32 Vacant Sub Centers)

Staff Nurses for Mother child care center at Medical College =  08

Financial Year 2013-14

. 	Budget :  97.68 Lakhs @ Rs 10000 / month/ ANM & @ Rs 14000/month/Staff nurse

2) Salary of ANMTC Tutor on contract

In District Pauri Garhwal one ANMTC is established at Khirsu.  Presently 03 Nos of batches are running at ANMTC. Present Staff consists of just  01 Nos of Regular Staff. Next year District is planning to appoint two Contractual Tutors.

| Issue | Rate | Req. |  | Amount |
| --- | --- | --- | --- | --- |
| Salary of ANMTC Tutor | Rs. 18,000 per month / tutor | 02 | 02x18000x12 | 432000 |

- PROGRAMME MANAGEMENT RELATED MATTERS

- District PMU Additional Manpower Requirement under NRHM.

Strengthening the District Programme management Unit:

| S.No | Head | Total Requirement |
| --- | --- | --- |
| 1 | DPMU Salary (DPM,.DAM,DDA) | 1256000.00 |
| 2 | Other (Mobility Support, Contingency etc | 240000.00 |
|  | Total | 1496000.00 |

B BLOCK PMU (SALARY, MOBILITY AND CONTINGENCY) - 15 BPMU Units are functional in District Pauri Garhwal.

| Sl. | Head | No. of BPHC's | No Of Months | Total Requirement |
| --- | --- | --- | --- | --- |
| 1 | Salary of BLM (18,000) | 15 | 12 | 3240000.00 |
| 2 | Salary of BLA (15000) | 15 | 12 | 2700000.00 |
| 3 | Salary of DEO (6000) | 15 | 12 | 1080000.00 |
| 4 | Contingency /Print & Stationery (20000) | 15 | 12 | 300000.00 |
| 5 | TA/DA of BPMU Staff | 15 | 12 | 225000.00 |
| 6 | Block level qtrly meetings | 60 | 12 | 120000.00 |
|  | Total |  |  | 7665000.00 |

- Institutionalizing Hospital Management Society/ (Rogi Kalyan Samiti).

| Activities: | - Identifying the problems faced by the patients in CHC/ PHC. - Acquiring equipment, furniture, ambulance (through purchase, donation, rental, or any other means, including loans, from banks) for the hospital - Expanding the hospital building, in consultation with and subject to any Guidelines that may be laid down by the State Government. - Making arrangements for the maintenance of hospital building (including residential buildings), vehicles and equipment available with the hospital. - Improving boarding/ lodging arrangements for the patients and their attendants - Entering into partnership arrangement with the private sector (including individuals) for the improvement of support services such as cleaning services, laundry services, diagnostic facilities and ambulatory services. - Developing/ leasing out vacant land in the premises of the hospital for commercial purposes with a view to improve financial position of the Society. - Encouraging community participation in the maintenance and upkeep of the hospitals - Promoting measures for resources conservation through adoption of wards by institutions and adopting sustainable and environmental friendly measures for the day-to-day management of the hospitals e.g. scientific hospitals waste disposal system, solar refrigeration systems, water harvesting and water re-charging systems. |
| --- | --- |

- Untied Fund to Sub centre.

| Activities: | - Placement of funds at the Sub-centre level to be jointly operated by the ANM and the Pradhan. - Involving the village Health & Sanitation committee to prepare priority based spending plans and keeping records of expenditure. - Engagement of part time cleaning personnel to be paid on daily wage basis. - For Purchasing Haemoglobin reagents. - Purchasing Photostat papers or Printing MCH/HMIS formats. |
| --- | --- |

- Untied Fund and Annual Maintenance Grant for CHCs/PHCs/APHCs.

| Activities: | - Till now 30 RKS have been formed at Block Level PHCs & 5 CHC’s. - Providing untied funds @Rs. 25,000 for PHC/APHC and @ 50000.00 for CHC. - Providing annual maintenance grant @Rs. 50,000 to PHC & @100000.00 to CHCs. - A separate register be maintained in the CHC/PHC giving sources of funds clearly for various activities. - PHC untied fund shall be kept in the bank account of the concerned Rogi Kalyan Samiti (RKS)/Hospital Management Committee (HMC). - PHC level Panchayat Committee/Rogi Kalyan Samiti will undertake and supervise the work to be undertaken from Annual Maintenance Grant. - Funds will be spent and monitored by RKS. Suggested areas where Untied Fund may be used : - Minor modifications to the Center- curtains to ensure privacy, repair of taps, installation of bulbs, other minor repairs, which can be done at the local level. - Provision of running water supply. - Provision of electricity. - Adhoc payments for cleaning up the Centre, especially after child birth. - Transport of emergencies to appropriate referral centres. - Transport of sample during epidemics. - Purchasing Printer Cartridges and contingencies. The Annual Maintenance Grant for PHCs may be utilized for the following : - The repairs & renovations on the basis of Facility Survey. - Small construction work such as boundary wall, grilling etc. - OT renovation, Tiling work etc. - Any type of work suitable for patient decide by Rogi Kalyan Samities. |
| --- | --- |

- Up-Gradation of CHC to IPHS.

| Activities: | - Facility survey of CHCs in respect of infrastructure, manpower and equipments. - Developing details plans for all the units FRUs along with construction agencies and initiating. - Procurement of equipment and instrument. - Establishing link with mother blood bank. - Provision of referral transport (Ambulance). - Strengthening of laboratory facilities. - Recruitment of MO’s & Para medical staff to meet CHC IPHS Standard. |
| --- | --- |

- Strengthening of District/Sub Divisional Hospitals.

| Activities: | - Induction training of a hospital manager into the hospital set-up. - Selection and induction of trained Paramedics especially Staff Nurses to District Head Quarter Hospital & Sub Divisional Hospitals. - Infrastructure up gradation of District Head Quarter Hospital/ Sub Divisional Hospitals. - Purchasing equipments for Patients benefit. |
| --- | --- |

- Village Health & Sanitation Committee.

| Activities: | - In District Pauri Garhwal 3112 Village Health & Sanitation Committee had been formed. - The grant can be used to carry out one or more out of the following activities as per the decision of the Committee. - Honorarium of sudurwarti swastshya sahayak @500/ month. - Preparation of village health plan and related activities. - Promotion of any village level public health activity like cleanliness drive, sanitation drive, school health activities, etc. - Disinfection of water sources, wells in the village, promote activities relating to mosquito eradication. - Organization of Health Mela, Sishu Mela, camp for the handicapped etc. - Providing emergency health services to old, infirm, destitute, orphan or handicapped persons belonging to poorer households of the village. - Creating awareness about good sanitary practices amongst adolescent girls and mothers. - Promotion of use of safe & clean drinking water and conducting water quality survey etc. - Discourage unsafe health practices and to encourage people to adopt accepted health practices instead of depending on quacks & untrained health care providers. - Discuss every maternal death & neonatal death that occurs in their village, analyse it and suggest necessary action to prevent such deaths & get them registered in the Panchayat. |
| --- | --- |

Budget :

| E | Untied Funds, AMG and RKS funds |  |  |
| --- | --- | --- | --- |
| 1 | Rogi Kalyan Samiti- DH | 1000000 | RKS Funds to 02 DH; |
| 2 | Rogi Kalyan Samiti- SDH | 200000 | RKS Funds to 2 SDH |
| 3 | Rogi Kalyan Samiti- CHC | 500000 | RKS Funds to 5 CHC IPHS |
| 4 | Rogi Kalyan Samiti-PHC/APHC | 3000000 | RKS Funds to 30 PHC |
| 5 | Untied Fund for CHC | 250000 | Untied Funds to 5CHC |
| 6 | Untied Fund for PHC | 800000 | Untied Funds to 30 PHC; |
| 7 | Untied Fund for SC | 2390000 | Untied Funds to 218 + 21 AAG SC |
| 8 | Untied Fund for VHSC | 31120000 | Untied Funds to 3112 VHSCs |
| 9 | Untied fund for ANMTCs | 100000 | Untied Funds to 1 ANMTC |
| 10 | Annual Maintenance Grant -DH | 0.00 |  |
| 11 | Annual Maintenance Grant -CHC | 500000 | AMG Funds to 5 CHC |
| 12 | Annual Maintenance Grant -BPHC | 500000 | AMG Funds to 10 Block level PHC |
| 13 | Annual Maintenance Grant -APHC | 800000 | AMG Funds to 16 PHC |
| 15 | Annual Maintenance Grant -SC | 770000 | AMG Funds to 77 SCs |
| 16.1.a | Upgradation of DH to IPHS | 1000000 | IPHS For DH |
| 16.2 | Upgradation of SDH to IPHS | 1000000 | IPHS For 02 SDH |
| 17 | Construction of 5 New Sub Center | 12000000 | 5 Sub center |
|  | SUB TOTAL | 55930000.00 |  |

9. ROUTINE IMMUNISATION:

- India’s Immunization Program is one of the largest in the world in terms of quantities of vaccines used, numbers of beneficiaries, and the numbers of immunization sessions organized, the geographical spread and diversity of areas covered. Under the immunization program, six vaccines are used to protect children and pregnant mothers against Tuberculosis, Diphtheria, Pertussis, Polio, Measles and Tetanus.  It is also proposed to include Hepatitis B vaccine in UIP in phased manner.

- Objective:

- To achieve 100% routine immunization coverage at right age in the district Pauri.

- To reduce mortality and morbidity due to vaccine preventable diseases (VPDs).

- Delivering effective and safe vaccines through an efficient delivery system.

Immunization Coverage in last eight Years.

Pulse Polio Achievements in last seven Years.

| SNID Year | Activity |  |
| --- | --- | --- |
|  | SNID % | NID % |
| 2005 | 100.6 | 99.7 |
| 2006 | 105 | 104.7 |
| 2007 | 103.2 | 96.7 |
| 2008 | 115.16 | 96.9 |
| 2009 | 126.5 | 97.25 |
| 2010 | 106.48 | 99.06 |
| 2011 | 129.83 | 100.72 |
| 2012 | 129.62 | 103.4 |

NID

- Strategies:

- Complete immunization coverage in the District will be improved by reducing the drop-out rates between doses, by reaching the children not-at-all immunized particularly those from low-income families and by addressing issues related to inter-district variations in performance. Information systems will be strengthened to identify children dropping out and proper follow up mechanisms will be established to cover them. Community help and assistance will be sought in identifying and mobilizing those children not covered by immunization programme at all. Administrative and resource constraints faced by low performing districts will be identified and addressed.

- Improved Registration System (CASE DETECTION).

- Improved Immunization Sessions.

- Improved Supervision System.

- Adequate Vaccine & Logistic, Available at all Level.

- Increased Awareness and Decreased Discrimination.

- Improved Accessibility Through Public Private Partnership.

- Programme Management (office Expenses) Ensured.

- Improve Recording of Records.

- Improved Disposal of Waste.

- Training of Cold Chain Maintenance of Doctors and staff.

- .

- Activities:

- Improved registration system( CASE DETECTION )

- Early registration of ANC.

- Incentive to ASHA for early ANC registration and after completion of two T.T. Dose.

- Training of ASHA.

- Training of ANM.

- Improved immunization sessions.

- Pre hand information of women/children to be immunised on vaccination session.

- Incentive to ASHA for bringing a child for vaccination(after complete immunization)

- Vaccine transportation from PHC/ CHC to sub center and back.

- Logistic transport from PHC/ CHC to sub center.

- Fixed day of immunization in spite of holidays.

- To improve coverage by increasing the access through Govt. facilities.

- Improved supervision system.

- Training of supervisors for supervision.

- Supervisory check list.

- Transportation facility/ T.A ,D.A

- Adequate vaccine & logistic, available at all level

- Training of MOIC & IO’S for vaccine and logistic procurement. (when/how).

- Individual may be hired for keeping vaccines for short period on payment basis through Panchayat/VHSC.

- Increased awareness and decreased discrimination.

- IEC

- Posters

- Cable Network

- Improved accessibility through public private partnership.

- Unserved area / under served area.

- To increase immunization coverage in inaccessible areas.

- To Encourage Mother for immunization.

- Motivating mother By ASHA, AWW & Dia. For This Purpose they should provide extra incentive.

- Mobilization of Children by ASHA/AWW to immunization Site with Mother.

- Motivating villagers especially mothers to keep Saturday as off day for the household works to bring their children to the identified centres.

- Improve recording of records.

- Training of ANM’s.

- Improved disposal of waste.

- Training of ANM’s.

- Waste transportation to PHC/CHC.

- Three Colour Bags (Red, Yellow, Black) should be Placed in each CHC/PHC/Hospitals.

- Cold chain maintenance

- Strengthening the Cold Chain Systems.

- Training of cold chain maintenance of doctors.

- Solar operated fridge can be given to such sub centres, which are off rout.  For other sub-centres small fridge may be arranged especially to the villages having more then 10 km distance.

- Oxygen cylinders and drug kits will be provided for management of anaphylaxis due to measles vaccine.

- Those already having it will be provided regular budget for refilling the cylinders.

- IEC for SNID’s in district level.

- By advertising in papers, Banners Etc.

- Monitoring & Evaluation.

- strengthening program management and supervision.

- Program evaluation.

- Systematic monitoring and accountability.

10. NATIONAL DISEASE CONTROL PROGRAMME:

The National Disease Control Programmes are being implemented in state under NRHM with a view to achieve the MDG goals to halt the spread of major diseases and reverse the trend by 2015 so as to reduce the mortality and morbidity and increase life expectancy and quality of life. The NDCP encompasses:  Revised National TB Control Programme (RNTCP), National Vector Borne Disease Control Programme (NVBDCP), and National Programme for control of Blindness (NPCB), The National Leprosy Eradication Programme (NLEP), Integrated Disease Surveillance Programme (IDSP), and Iodine Deficiency Disorder Control Programme (IDDCP).

  - RNTCP (Revised National TB Control Programme).

Tuberculosis  (TB)  an  infective  disease  caused  by  Mycobacterium  Tuberculosis,  which  spreads  from  a diseased  person  to  a  healthy  one.  Germs  of  TB  spread  through  air  when  untreated  patients  cough  or sneeze. TB mainly affects the lungs; but it can also affect other parts of the body (Brain, Bones, Glands, etc.).  The  Revised  National  Tuberculosis  Control  Programme  (RNTCP)  aims  to  stop  the  spread  of  TB  by curing patients. The key of this strategy is to cure TB through Directly Observed Treatment at a time and place convenient to the patient.

Goal: The goal of RNTCP is to decrease mortality and morbidity due to TB and cut transmission of infection

Until TB ceases to be a major public health problem.

Objective:

- To achieve and maintain a cure rate of at least 85% among newly detected infectious (new sputum smear positive) cases, and

- To achieve and maintain detection of at least 70% of such cases in the population...

ORGANIZATION OF SERVICES IN THE DISTRICT:

| S. No. | Name of the TU | Population (in Lakhs) | Please indicate if the TU is- |  | No. of MCs |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Govt | NGO | Govt | NGO | Private |
| 1 | TU Pauri | 2.78 | Yes |  | 9 |  |  |
| 2 | TU Dugadda | 2.32 | Yes |  | 6 |  |  |
| 3 | TU Bironkhal | 1.88 | Yes |  | 6 |  |  |
|  | DISTRICT | 6.98 |  |  | 21 |  |  |

RNTCP performance indicators:

Important: Please give the performance for the last 4 quarters i.e. October 2010 to September 2011

| TB Unit | Total number of patients put on treatment | Annualized total case detection rate (per lakh pop) | No of new smear positive cases put on treatment | Annualized New smear positive case detection rate (per lakh p op) | Cure rate for cases detected in the last 4 corresponding quarters | Plan for the next year |  | Proportion of TB patients tested for HIV |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Annualized NSP CDR | Cure rate |  |
| Pauri | 315 | 113 | 124 | 45 | 76% | 75% | 90% | 118/2 |
| Dugadda | 419 | 181 | 175 | 75 | 81% | 75% | 90% | 195/5 |
| Bironkhal | 222 | 118 | 75 | 40 | 78% | 75% | 90% | 71/0 |

#### Section B – List Priority areas for achieving the objectives planned:

| S.No. | Priority areas | Activity planned under each priority area |
| --- | --- | --- |
| 1 | Area around Combind Hospital Kotdwara | 1 a)Regular Follow-up sputum examnination. |
|  |  | 1 b)Beter supervision |
|  |  | 1 c) Continuity to take medicine |
| 2 | Area around Distt .Hospital Pauri | 2 a)Quality maintenance to Lab for sputum examination. |
|  |  | 2 b) Better case detection |
| 3 | Area in TU Bironkhal | 1 ASHAs training For better case detection |
|  |  | 2. Patients Provider meeting |
| 4 | Drugs Availability in Each T. U | 1. Proper supply of DOTS medicine in each T.U. |
| 5 | Area around chakisain | 1. ASHAs training for more sputum examination, because in this area there are more patients. |
| 6 | Supervision in entire district | Better Supervision of treatment in entire district along with DOTS Plus treatment. (PMDT) |

##### Section C – Plan for Performance and Expenditure under each head:

Civil Works

| ##### Activity | ##### No. required as per the norms in the district | ##### No. actually present in the district | ##### No. planned for this year | ##### Pl provide justification if an increase is planned (use separate sheet if required) | ##### Estimated Expenditure on the activity | ##### Quarter in which the planned activity expected to be completed |
| --- | --- | --- | --- | --- | --- | --- |
|  | ##### (a) | ##### (b) | ##### (c) | ##### (d) | ##### (e) | ##### (f) |
| ##### DTC | ##### 1 | ##### 1 | ##### - | ##### - | ##### 30000.00 | ##### 3q 2013 |
| ##### TUs | ##### 3 | ##### 3 | ##### - | ##### - | ##### 30000.00 | ##### 3q2013 |
| ##### DMC | ##### 21 | ##### 21 | ##### - | ##### - | ##### 20000.00 | ##### 3q 2013 |
| ##### Total |  |  |  |  | ##### 80000.00 |  |

Laboratory Materials

| ##### Activity | ##### Amount permissible as per the norms in the district | ##### Amount actually spent in the last 4 quarters | ##### Procurement planned during the current financial year (in Rupees) | ##### Estimated Expenditure for the next financial year for which plan is being submitted ##### (Rs.) | ##### Justification/ Remarks for (d) |
| --- | --- | --- | --- | --- | --- |
|  | ##### (a) | ##### (b) | ##### (c) | ##### (d) | ##### (e) |
| ##### Purchase of Lab Materials | 117000.00 | ##### 55621.00 | ##### 110000.00 | ##### 117000.00 |  |

Honorarium

| ##### Activity | ##### Amount permissible as per the norms in the district | ##### Amount actually spent in the last 4 quarters | ##### Expenditure (in Rs) planned for current financial year | ##### Estimated Expenditure for the next financial year for which plan is being submitted ##### (Rs.) | ##### Justification/ Remarks for (d) |
| --- | --- | --- | --- | --- | --- |
|  | ##### (a) | ##### (b) | ##### (c) | ##### (d) | ##### (e) |
| ##### Honorarium for DOT providers (both tribal and non tribal districts) | ##### 87750.00 | ##### 80500.00 | ##### 87750.00 | 87750.00 |  |
| ##### Honorarium for DOT providers of Cat IV patients |  | ##### 0.00 | ##### 0.00 | 20000.00 |  |

Annual Action Plan Format Advocacy, Communication and Social Mobilization (ACSM) for RNTCP

- Information on previous year’s Annual Action Plan

  - Budget proposed in last Annual Action Plan:   70000.00

  - Amount released by the state: 50000.00

  - amount Spent by the district- 12766.00

  - Permissible budget as per norm :  78500.00

- Budget for next financial year for the district as per action plan detailed below: …60000.00

| Program Challenges to be tackled by ACSM during the Year 2012-13 | WHY ACSM Objective | For WHOM Target Audience | WHAT ACSM Activities |  | When Time Frame |  |  |  |  | By WHOM |  | Monitoring and Evaluation |  | Budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Based on existing TB indicators and analysis of communication challenges (Maximum 3 Challenges ) | Desired behavior or action (make SMART: specific, measurable, achievable, realistic & time bound objectives) |  | Activities | Media/ Material Required | Q1 | Q2 | Q3 |  | Q4 | Key implementer and RNTCP officer responsible for supervision |  | Outputs; Evidence that the activities have been done | Outcomes: Evidence that it has been effective | Total expenditure for the activity during the financial year |
| Challenge 1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Advocacy Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Awareness | IPC, CME | Health Care | IEC | Poster Pomplets, Booklets |  |  |  |  |  | DTO |  | MOTC, STS |  | 5000.00 |
| Communication Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Folk Media Local Channel Local Mela | PHI | Patient & Family | IEC CME | Patient Provider Meeting | 2 | 2 | 3 |  | 3 | DTO |  |  |  | 5000.00 |
| Social Mobilization activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Worker Gram Pradhan BDC Member | Health Staff | Community Meeting Patient Provider Meeting | IEC | Meeting | 3 | 3 | 3 |  | 3 | DTO |  | MOTC STS |  | 10000.00 |
| Challenge 2: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Advocacy Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Awareness | IEC | Community Volunteers Social Workers | IEC | Poster Pomplets Banners | 2 | 2 | 2 |  | 2 | DTO |  | MOTC STS |  | 10000.00 |
| Communication Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Folk Media Local Channel Local Melas | Health Staff | Patient their family | IEC | Media Martial | 2 | 2 | 2 |  | 2 | DTO |  | MOTC STS |  | 5000.00 |
| Social Mobilization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Awareness | IEC, CME | Patient Provider Meeting | IEC | Meeting Patient provider meeting | 2 | 2 | 2 |  | 2 | DTO |  | MOTC STS |  | 10000.00 |
| Challenge 3:- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Advocacy activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Awareness | IEC | Wall Painting | IEC | Poster Wall Painting | 3 | 2 | 3 |  | 2 | DTO |  |  |  | 5000.00 |
| Communication activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Folk Media Local Mela | IEC | Meeting | IEC | IEC | 2 | 2 |  | 2 |  | 2 | DTO |  |  | 5000.00 |
| Social Mobilization Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Awareness | IEC | Patient Provider meeting | IEC | IEC | 2 | 2 | 2 |  | 2 | DTO |  |  |  | 5000.00 |
| TOTAL BUDGET |  |  |  |  |  |  |  |  |  |  |  |  |  | 60000.00 |

Comments, if any:-                                                                                                                                                                             Prepared by:- S.D.T.O

Equipment Maintenance:

| ##### Item | ##### No. actually present in the district | ##### Amount actually spent in the last 4 quarters | ##### Amount Proposed for Maintenance during current financial yr. | ##### Estimated Expenditure for the next financial year for which plan is being submitted ##### (Rs.) | ##### Justification/ Remarks for (d) |
| --- | --- | --- | --- | --- | --- |
|  | ##### (a) | ##### (b) | ##### (c) | ##### (d) | ##### (e) |
| ##### Office Equipment ##### (Maintenance includes computer software and hardware upgrades, repairs of photocopier, fax, OHP etc) | ##### 1 Each | ##### 18305.00 | ##### 30000.00 | ##### 40000.00 |  |
| ##### Binocular Microscopes ( RNTCP) |  |  |  |  |  |

Training:

| ##### Activity | ##### No. in the district | ##### No. already trained in RNTCP | ##### No. planned to be trained in RNTCP during each quarter of next FY ##### (c) |  |  |  | ##### Expenditure (in Rs) planned for current financial year | ##### Estimated Expenditure for the next financial year for which plan is being submitted ##### (Rs.) | ##### Justification/ remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | ##### Q1 Q2 Q3 Q4 |  |  |  |  |  |  |
|  | ##### (a) | ##### (b) |  |  |  |  | ##### (d) | ##### (e) | ##### (f) |
| ##### Training of MOs | ##### 250 | ##### 33 | ##### 50 | ##### 50 | ##### 50 | ##### 50 | ##### 42900.00 | ##### 45000.00 |  |
| ##### Training of LTs of DMCs- ##### Govt + Non Govt | 23 | ##### 23 | ##### 0 | ##### 0 | ##### 0 | ##### 0 |  |  |  |
| ##### Training of MPWs | ##### 45 | ##### 20 | ##### 0 | ##### 0 | ##### 20 | ##### 0 |  |  |  |
| ##### Training of MPHS, pharmacists, ##### nursing staff, BEO etc | 120 | 80 | ##### 0 | ##### 0 | ##### 20 | ##### 20 |  |  |  |
| ##### Training of Comm Volunteers | ##### 1123 | ##### 1123 | ##### 0 | ##### 0 | ##### 0 | ##### 0 |  |  |  |
| ##### Training of Pvt Practitioners | ##### 0 | ##### 0 | ##### 0 | ##### 0 | ##### 0 | ##### 0 |  |  |  |
| ##### Other trainings # | ##### - | ##### - | ##### - | ##### - | ##### - | ##### - | ##### - |  |  |
| ##### Re- training of MOs | ##### 250 | ##### 33 | ##### - | ##### - | ##### - | ##### - |  |  |  |
| ##### Re- Training of LTs of DMCs | ##### 23 | ##### 23 | ##### - | ##### 10 | ##### 13 | ##### - |  |  |  |
| ##### Re- Training of MPWs | ##### - | ##### - | ##### - | ##### - | ##### - | ##### - |  |  |  |
| ##### Re- Training of MPHS | ##### - | ##### - | ##### - | ##### - | ##### - | ##### - |  |  |  |
| ##### Re- Training of Pharmacists | ##### - | ##### - | ##### - | ##### - | ##### - | ##### - |  |  |  |
| ##### Re- Training of nursing staff, BEO | ##### - | ##### - | ##### - | ##### - | ##### - | ##### - |  |  |  |
| ##### Re- Training of CVs | ##### - | ##### - | ##### - | ##### - | ##### - | ##### - |  |  |  |
| ##### Re-training of Pvt Practitioners | ##### - | ##### - | ##### - | ##### - | ##### - | ##### - |  |  |  |
| ##### TB/HIV Training of MOs | ##### 250 | ##### 33 | ##### 50 | ##### 50 | ##### 50 | ##### 50 |  |  |  |
| ##### TB/HIV Training of STLS, LTs , MPWs, MPHS, Nursing Staff, Community Volunteers etc | - | ##### - | - | - | - | - |  |  |  |
| ##### TB/HIV Training of STS | ##### 2 | ##### 2 | ##### 0 | ##### 2 | ##### 0 | ##### 2 |  |  |  |
| ##### Training of MOs and Para medicals in DOTS Plus for management of MDR TB | ##### 814 | ##### 125 | ##### 100 | ##### 100 | ##### 100 | ##### 100 |  |  |  |
| ##### Provision for Update Training at Various Levels(key staff & MO-PHIs) | ##### - | ##### - | ##### - | ##### - | ##### - | ##### - |  |  |  |
| ##### Any Other Training Activity( Key staff & MO-PHIs) | ##### - | ##### - | ##### - | ##### - | ##### - | ##### - |  |  |  |

#  Please specify

Vehicle Maintenance:

| ##### Type of Vehicle | ##### Number permissible as per the norms in the district | ##### Number actually present | ##### Amount spent on POL and Maintenance in the previous 4 quarters | ##### Expenditure (in Rs) planned for current financial year | ##### Estimated Expenditure for the next financial year for which plan is being submitted ##### (Rs.) | ##### Justification/ remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  | ##### (a) | ##### (b) | ##### (c) | ##### (d) | ##### (e) | ##### (f) |
| ##### Four Wheelers | ##### 1 | ##### 1 | ##### 67926.00 | ##### 125000.00 | ##### 125000.00 |  |
| ##### Two Wheelers | ##### 3 | ##### 3 | ##### 145761.00 | ##### 70000.00 | ##### 70000.00 |  |

Vehicle Hiring:

| ##### Hiring of Four Wheeler | ##### Number permissible as per the norms in the district | ##### Number actually present | ##### Amount spent in the previous 4 quarters | ##### Expenditure (in Rs) planned for current financial year | ##### Estimated Expenditure for the next financial year for which plan is being submitted (Rs.) | ##### Justification/ remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  | ##### (a) | ##### (b) | ##### (c) | ##### (d) | ##### (e) | ##### (f) |
| ##### For DTO | ##### 1 | ##### - | ##### - | ##### - | ##### - |  |
| ##### For MO-TC | ##### 3 | ##### - | ##### 0.00 | ##### 120000.00 | ##### 100000.00 |  |

NGO/ PP Support: (New schemes w.e.f. 01-10-2008)

| ##### Activity | ##### No. of currently involved in RNTCP in the district | ##### Additional enrolment planned for this year | ##### Amount spent in the previous 4 quarters | ##### Expenditure (in Rs) planned for current financial year | ##### Estimated Expenditure for the next financial year for which plan is being submitted ##### (Rs.) | ##### Justification/ remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  | ##### (a) | ##### (b) | ##### (c) | ##### (d) | ##### (e) | ##### (f) |
| ##### ACSM Scheme: TB advocacy, communication, and social mobilization | ##### - | ##### - | ##### - | ##### - | ##### - |  |
| ##### SC Scheme: Sputum Collection Centre/s | ##### - | ##### - | ##### - | ##### - | ##### - |  |
| ##### Transport Scheme: Sputum Pick-Up and Transport Service | ##### - | ##### - | ##### - | ##### - | ##### - |  |
| ##### DMC Scheme: Designated Microscopy Cum Treatment Centre (A & B) | ##### - | ##### - | ##### - | ##### - | ##### - |  |
| ##### LT Scheme: Strengthening RNTCP diagnostic services | ##### - | ##### - | ##### - | ##### - | ##### - |  |
| ##### Culture and DST Scheme: Providing Quality Assured Culture and Drug Susceptibility Testing Services | ##### - | ##### - | ##### - | ##### - | ##### - |  |
| ##### Adherence scheme: Promoting treatment adherence | ##### - | ##### - | ##### - | ##### - | ##### - |  |
| ##### Slum Scheme: Improving TB control in Urban Slums | ##### - | ##### - | ##### - | ##### - | ##### - |  |
| ##### Tuberculosis Unit Model | ##### - | ##### - | ##### - | ##### - | ##### - |  |
| ##### TB-HIV Scheme: Delivering TB-HIV interventions to high HIV Risk groups (HRGs) | ##### - | ##### - | ##### - | ##### - | ##### - |  |
| ##### TOTAL |  |  |  |  |  |  |

Miscellaneous:

| ##### Activity* | ##### Amount permissible as per the norms in the district | ##### Amount spent in the previous 4 quarters | ##### Expenditure (in Rs) planned for current financial year | ##### Estimated Expenditure for the next financial year for which plan is being submitted ##### (Rs.) | ##### Justification/ remarks |
| --- | --- | --- | --- | --- | --- |
|  | ##### (a) | ##### (b) | ##### (c) | ##### (d) | ##### (e) |
|  | ##### 117000.00 | ##### 197467.00 | ##### 117000.00 | ##### 117000.00 |  |

* Please mention the main activities proposed to be met out through this head

Contractual Services:

| ##### Activity | ##### No. required as per the norms in the district | ##### No. actually present in the district | ##### No. planned to be additionally hired during this year | ##### Amount spent in the previous 4 quarters | ##### Expenditure (in Rs) planned for current financial year | ##### Estimated Expenditure for the next financial year for which plan is being submitted ##### (Rs.) | ##### Justification/ remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | ##### (a) | ##### (b) | ##### (c) |  | ##### (d) | ##### (e) |  |
| ##### Medical Officer-DTC | ##### Not to be filled | ##### - | ##### - | ##### 0.00 | ##### - | ##### - |  |
| ##### STS | ##### 3 | ##### 3 | ##### - | ##### 478800.00 | ##### 730000.00 | ##### 600000.00 |  |
| ##### STLS | ##### 3 | ##### 3 | ##### - | ##### 440000.00 | ##### 550000.00 | ##### 450000.00 |  |
| ##### TBHV | ##### 2 | ##### 2 | ##### - | ##### 220000.00 | ##### 250000.00 | ##### 270000.00 |  |
| ##### DEO | ##### 1 | ##### 1 | ##### - | ##### 117000.00 | ##### 150000.00 | ##### 160000.00 |  |
| ##### Accountant – part time | ##### 1 | ##### - | ##### - | ##### 0.00 | ##### - | ##### - |  |
| ##### Contractual LT |  | ##### 9 | ##### - | ##### 1055000.00 | ##### 1200000.00 | ##### 1300000.00 |  |

Printing:

| ##### Activity | ##### Amount permissible as per the norms in the district | ##### Amount spent in the previous 4 quarters | ##### Expenditure (in Rs) planned for current financial year | ##### Estimated Expenditure for the next financial year for which plan is being submitted ##### (Rs.) | ##### Justification/ remarks |
| --- | --- | --- | --- | --- | --- |
|  | ##### (a) | ##### (b) | ##### (c) | ##### (d) | ##### (e) |
| ##### Printing* | ##### - | ##### - | ##### - | ##### - |  |

* Please specify items to be printed

Research and Studies:

Any Operational Research project planned (Yes)

(Post Graduate grant for one research paper from each Medical College)

Estimated Budget (to be approved by STCS).___________________________________

Medical Colleges

| ##### Activity | ##### Amount permissible as per norms | ##### Estimated Expenditure for the next financial year(Rs.) | ##### Justification/ remarks |
| --- | --- | --- | --- |
|  | ##### (a) | ##### (b) | ##### (c) |
| ##### Contractual Staff: ##### MO (In place: Yes/No) No ##### STLS (In place: Yes/No) No ##### LT (In place: Yes/No) Yes ##### TBHV (In place: Yes/No) No | - | - |  |
| ##### Research and Studies: - Thesis of PG Student - Operations Research* | - |  |  |
| ##### Travel Expenses for attending STF/ZTF meetings | ##### - | ##### 25000.00 |  |
| ##### IEC: Meetings and CME planned | ##### - | ##### 25000.00 |  |
|  | ##### - | ##### 50000.00 |  |

Procurement of Vehicles:

| ##### Equipment | ##### No. actually present in the district | ##### No. planned for this year | ##### Estimated Expenditure for the next financial year for which plan is being submitted (Rs.) | ##### Justification/ remarks |
| --- | --- | --- | --- | --- |
|  | ##### (a) | ##### (b) | ##### (c) | ##### (d) |
| ##### 4-wheeler ** | ##### 1 | ##### - | ##### - |  |
| ##### 2-wheeler | ##### 3 | ##### - | ##### - |  |

** Only if authorized in writing by the Central TB Division

Procurement of Equipment:

| ##### Equipment | ##### No. actually present in the district | ##### No. planned for this year | ##### Estimated Expenditure for the next financial year for which plan is being submitted (Rs.) | ##### Justification/ remarks |
| --- | --- | --- | --- | --- |
|  | ##### (a) | ##### (b) | ##### (c) | ##### (d) |
| ##### Office Equipment (computer, modem, scanner, printer, UPS etc) | ##### 1 Each | ##### - | ##### - |  |
| ##### Any Other |  |  |  |  |

##### Section D: Summary of proposed budget for the district –

| S.No. | Category of Expenditure | Budget estimate for the coming FY 2010- 11 |
| --- | --- | --- |
|  |  | (To be based on the planned activities and expenditure in Section C) |
| 1 | Civil works | 80000.00 |
| 2 | Laboratory materials | 117000.00 |
| 3 | Honorarium | 107750.00 |
| 4 | IEC/ Publicity | 60000.00 |
| 5 | Equipment maintenance | 40000.00 |
| 6 | Training | 45000.00 |
| 7 | Vehicle maintenance | 195000.00 |
| 8 | Vehicle hiring | 100000.00 |
| 9 | NGO/PP support | 0.00 |
| 10 | Miscellaneous | 117000.00 |
| 11 | Contractual services | 2975000.00 |
| 12 | Printing | 0.00 |
| 13 | Research and studies | 0.00 |
| 14 | Medical Colleges | 50000.00 |
| 15 | Procurement –vehicles | 0.00 |
| 16 | Procurement – equipment | 0.00 |
|  | TOTAL | 3886750.00 |

  - NVBDCP (National Vector Borne Disease Control Programme).

NVBDCP includes major vector borne diseases of public Health importance, such as Malaria, Filariasis, Japanese Encephalitis, Dengue, and Kala azar.

The goal of NVBDCP is identify vulnerable areas for malaria. But now a days Dengue are observed in the district, so it is important to identify sensitive pockets for these diseases. In Pauri district no incidence of Filaria/Kala Azar/J.E.are notified in the district.

| Disease | 2008-09 | 2009-10 | 2010-11 | 2011-12 | 2012-13 |
| --- | --- | --- | --- | --- | --- |
| Malaria cases Examined(Positive) | 31764 (4) | 31785 (18) | (21485)17 | 11917(88) | 10596(54) |
| Dengue | 9 | - | 76 | 2 | 13 |
| CHK | - | - | - | - |  |
| Filaria | - | - | - | - |  |
| J.E. | - | - | - | - |  |
| Kala azar | - | - | - | - |  |

Goal: Detection of malaria cases up to 100% by 2013.

Objective:

- To increase the coverage of prevention interventions for vector borne disease amongst population

- Enhance the access to early diagnosis & complete treatment

- Strengthen the technical & managerial capacity of the vector borne disease control programme.

- Increase the visibility & vector borne disease control programme

- Output based monitoring of the control programme.

- Create awareness in the community regarding NVBDC programme by utilization ASHA/AWW.

Strategies and Activities:

- EDPT (Early Diagnosis and Prompt Treatment)

  - Establishment of DDC (Drug Distribution Centre), FTD (Fever Treatment Depots), MLV (Malaria Link Volunteers).

  - Identification of high risk and vulnerable areas.

  - Additional manpower for surveillance & B.S. examination as per requirement.

  - Additional manpower for spraying & fogging.

  - Regular surveillance by health worker.

- Selective vector control.

  - IRS/focal spraying are carried out in 3-4 blocks of the districts where high incidence of malaria is observed due to labour movement and borderline area.

  - Antilarval spraying is essential in Dengue prone area.

  - Fogging is essential in areas where Aedes egypti mosquito density is increased as well as in areas where Dengue outbreak situation is observed to reduce burden of the disease.

- Other Activities.

  - IEC activities like posters exhibitions, announcing through the cable/ radio network, making, seasonal greeting, handbills, slogans, dramas is essential.

  - For the participation of different departments in vector borne disease control programme coordination meetings/workshops are organized timely to get maximum participation from these departments.

  - In NVBDCP different vector borne diseases are included and for better implementation of control measures training to regular staff, NGOs is essential.

  - Monitoring and evaluation of the programme is essential in the whole district throughout the year.

- CMIS (Computerised Management Information System).

  - For prompt and smooth flow of information from grass root level to identify operational problems so as to take necessary remedial measures, specially designed software has been provided to all districts and operators have been trained for on-line data entry of monthly epidemiological status.

| Budget Requirement (NVBDCP) for the year 2013- 14 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sl No. | Activity | Details | Requirement | Unit Cost in Rs |  | Unit Cost in Rs. | Total Expenditure (Rs In Lacks) |
|  |  |  | Name of Units | Number |  |  |  |
| 1 | Early Detection & Prompt Treatment | RD test Kits ( for Trible/remote areas and epidemic/Pf prone areas) | PHC/CHC | 9500 test |  | 100 | 9.5 |
|  |  | Wages contractual MPW male | PHC/CHC | 120 MPW |  | 10000 | 144.0 |
|  |  | Incentive to ASHA for B/S collection | BLOCK | 15 |  | 60000 | 9.0 |
|  |  | Incentive to ASHA for PV RT | PHC/CHC | 100 case |  | 100 | 0.10 |
|  |  | Incentive to ASHA for PT RT | PHC/CHC | 10 case |  | 100 | 0.01 |
| 2 | TRS | DDT 50 ml |  |  |  |  |  |
| 3 | Antilarval/ Adulticidal Measures in urban and port urban areas | Abate | Liter | 100 Litre |  | 2000 | 2.0 |
|  |  | Pyrethrum Extract 2 % ( Ready to use) | Liter | 200 Litre |  | 400 | 0.80 |
| 4 | Monitoring & Supervision | POL/Hiring off Vehicle | Days | 200 Day |  | 2000 | 4.0 |
| 5 | IEC/BCC | Developing creative and implementing IEC activities as per action plan | Miking, Pumplet, poster, Banner, News paper | 15 PHC/CHC |  | 60000 | 9.0 |
| 6 | Capacity Building | MO PHC |  |  |  |  |  |
|  |  | LT |  |  |  |  |  |
|  |  | MPW (Contractual) | Training | 4 Batch |  | 30000 | 1.2 |
|  |  | Health Workers female | Training | 4 Batch |  | 30000 | 1.2 |
|  |  | ASHA | Training | 15 Batch |  | 25000 | 7.5 |
|  |  | State level quarterly review meeting |  |  |  |  |  |
| 7 | NAMMIS | Computer system with printer, cartridge etc. & Photostat machine | Computer, Printer, Cartridge, Photo state machine - | 1 |  | 150000 | 1.5 |
|  |  | Data entry operator district level ( as per govt of U.K guideline) | 1 Data Entry operator | 1 |  | 150000 | 1.50 |
|  |  | Sub Total |  |  |  |  |  |
|  |  | GRAND TOTAL |  |  | 19.61 Lacks |  |  |

c. NLEP (Leprosy Eradication Programme).

SITUATION ANALYSIS:

Staff Position :

DLO 	in charge 				1                                         Educationist. 					1

NMS						1                                         Ward Boy					1

Driver 					1                                         Clerk 						0

Indicators.

| Sno | Particular | 2006-07 | 2007-08 | 2008-09 | 2009-10 | 2010-11 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | ANCDR | 0.73 | 0.74 | 1.09 | 0.39 | 0.34 |
| 2 | P.R | 0.76 | 0.57 | 0.43 | 0.36 | 0.36 |
| 3 | Disability Grade II | 0 | 0 | 0 | 0 | 0 |
| 4 | T.C.R | 73% | 75% | 79% | 80.7% | 75% |
| 5 | Reconstructive surgery | 0 | 0 | 0 | 0 | 0 |

Brief description of block wise cases till Nov 2011

| S.no | Name of Block | Population |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | MB | PB | Total |
| 1 | Duggada | 104284 | 4 | 1 | 5 |
| 2 | Dadamandi | 41408 |  |  |  |
| 3 | Khirsoo | 47263 | 1 |  | 1 |
| 4 | Pabu | 36902 | 1 | 1 | 2 |
| 5 | Parsundakhal | 59021 |  |  |  |
| 6 | Kot | 29519 |  |  |  |
| 7 | Thalisain | 52810 |  |  |  |
| 8 | Bironkhal | 40792 |  |  |  |
| 9 | Nanidanda | 44134 |  |  |  |
| 10 | Ghandyal | 34772 | 1 |  | 1 |
| 11 | Pokhra | 25128 |  |  |  |
| 12 | Pattisain | 32007 |  |  |  |
| 13 | Jharikhal | 39075 |  |  |  |
| 14 | Rihknikhal | 31870 |  |  |  |
| 15 | Yamkeshwar | 32493 |  |  |  |
|  | TOTAL |  | 7 | 2 | 9 |

TWO PAL COLONIES

1) Dhobi Ghat Srinagar.				3 ladies residing.

2) Nirmala Mata Ashram. Kotdwar		17 PAL with their families.

Dhobi Ghat Srinagar:

Encroachment by a Nepali with in their premises.

Geriatric problem.

Nirmala Mata Ashram. Kotdwar:

The water gets inside the room during rainy season.

Begging has been their bread and butter.

No entertainment.

Payment of electricity bill.

Encroachment of the road and surrounding by street pickers.

In Summary the situation of  N.L.E.P in Distt. Pauri Gharwal.

To eradicate leprosy in distt. Pauri Gharwal has by now achieved P.R of 0.36 per 10, 000 population. Though this figure may be better than the figure before but when it comes to number of cases it becomes about 10 cases at a given time. To find and treat these cases is a big challenge. Since  most of the cases are now concentrated in Shrinagar and Kotdwar.been now it is better to focus with more attention and effort in these two areas wile continuing the efforts in other area too

Well Trained staff: Regarding the N.L.E.P we have well trained Medical Officers ( both Allopathic and AYUSH) who have been trained at State level. All the Para medical staff (Pharmacist, Male & Female supervisors & A.N.M & L.T’s)  ASHA have been trained during their modular training and further MOIC have retrained them in their quarterly meetings so that no case is missed who so ever comes in the contact of our medical staff. Reorientation trainings of 100 ANM’s are been conducted this year to refresh their knowledge.

Referral Slips:  referral slips have been given to all the MOIC’s so that they can distribute them to ASHA & ANM.

Incentive to ASHA: ASHA is given incentive of rupees 100 at the time of referral of a leprosy case while rest sum of 300/- in PB and 500/- in MB are given to her after the completion of treatment. This year some case have been referred and one case treated by ASHA.

Logistic Support: all the PHC’s have been supplied with case register, drug stock register, deformity & reaction register, reporting Performa and contingency (paper A-4 size , files and folders, stapler and staples. Punch machine, pencil, rubber, eraser etc.).PHI where L.T ‘s are trained in microscopic examination are supplied with reagent.

Drug Management: It has been ensured that MDT is provided free of cost to patient by the drug counter so that the patient can easily get the medicine. Supportive drugs are also provided to the PHI so that each reaction cases can be treated according to their complaint. It was ensured that for each care there would be 4 MDT Blister Packets ( 2 at distt. And 2 at the treating center).

IEC: Two school rally & Two school quiz were performed and to the students sweets were distributed while prizes were distributed to the students who came in merit till 3 and pen were distributed to all of the students who participated. Puppet show and magic show were conducted in each and every block in Bazar or school involving MOIC of the block. Total of thirty IPC were conducted in the district 2 each by each MOIC of every block.

Meetings Of DLS and NGO’S: meeting with NGO’s and DLS is to be arranged for this year.

LAPER HOMES:

The state has thought for the benefits for PAL(patient affected from leprosy) they are given BPL ration card so that they get ration at a very low cost. PAL are given pension of rupees 1000/- pm in their postal account. They are also provided with Self care Kits and given training os that they can take care of their ulcers or injuries and themselves. Every week a visit of doctor of near by PHI is to visit to their home and see their requirement or help. People from the community come forward to help them and gift them sweets or food during any festivals or occasions. Their children are studying in nearby schools, college and doing some vocational training with fee. DPMR services are also being provided to them. There is no case for corrective operation.

Area of focus this year (2013-2014)

- Intensified IEC activities in Srinagar and Kotdwar .To promote self referral for early diagnosis. Increase in the awareness of the disease and bring about the reduction in the non-discriminatory attitude of the community & also take help of ASHA for referral and treatment.

- Intensify action in slum area and out reach area. Defaulters would be identified and put back into treatment.

- Counseling patient for self care activities and involvement of NGO’s.

SWOT ANALYSIS:

STRENGTH

- Infrastructure of health Facility.

- Well trained general health unit.(both medical and Paramedical)

- Timely Funding.

- Free cost MDT.

- School Health Programme.

- NRHM /RCH Camps.

- VHND.

- Quick feed back from the State.

WEAKNESS

- Some of the medical & Paramedical staff not residing at the headquater.

- Staff is not well motivated to their Job.

- Less co-ordination between the staff and the PRI’s.

- Referral system..

OPPORTUNITIES

- High Literacy rate among both male and female population.

- Most of the Population is Army/Ex –Army person or Government Servant.

- Political will towards health services is quite high.

- People demand and expectation for health services is quite high.

- Well established mobile telephonic facilities.

- Mobility is better by more of private than public transport.

- PRI are very active.

- Availability of ASHA in all village.

THREATS

- Non availability of Panchyat Adhikari at his office.

- Scattered Population.

- Hilly area.

- Difficult Weather conditions (winters and rainy seasons).

Objective and results:

RESULT 1:IMPROVED CASE DETECTION..

RESULT 1:IMPROVED CASE REFRAL & REPORTING SYSTEM.

RESULT 2:IMPROVED PROGRAMME MANAGEMENT ENSURED.

RESULT 3:IMPROVED MONITORING AND SUPERVISION SYSTEM

RESULT 4: IMPROVED ADIQUATE DRUGS SUPPORT AT ALL LEVEL

RESULT 5: IMPROVED SUPPORTIVE MANAGEMENT ENSURED.

RESULT 6:IMPROVED DPMR SERVICES.

RESULT 7:IMPROVED AWARENESS AND DECREASED DISCRIMNATION.

RESULT 8:  PROGRAMME MANAGEMENT ENSURED.

| S.NO |  | ACTIVITIES |
| --- | --- | --- |
| RESULT 1:IMPROVED CASE DETECTION. |  |  |
| 1.1 | Reorientation Training for block level MO’s./M.O in school health Programme. |  |
| 1.2 | Reorientation Training of left ANM. |  |
| 1.3 | Reorientation of Training of Pharmasyst’s at PHI. |  |
| 1.4 | Reorientation of Training of ASHA. |  |
| 1.5 | Training of Lab. Assistance. |  |
| 1.6 | C.M.E. programme in Srinagar, Kotdwar & Pauri. |  |

| RESULT 1:IMPROVED CASE REFRAL & REPORTING SYSTEM. |  |
| --- | --- |
| 2.1 | Referral slips and formats. |
| 2.2 | ASHA Incentives. |
| 2.3 | Incentives for cases on completion of treatment. |
| 2.4 | Road travel expenses for pt. on diagnosis to the PHI or the referring center. |
| 2.5 | Logistics and stationary. |

| S.NO | ACTIVITIES |
| --- | --- |
| RESULT 3:IMPROVED MONITORING AND SUPERVISION SYSTEM |  |
| 3.1 | Vehicle repair & POL |
| 3.2 | Quaterly review meetings with MO’s of PHI’s. |
| 3.3 | Supervision of group meetings. |
| 3.4 | Monthly visit at PHC/ CHC |
| 3.5 | Supervisory check list ; Feed back forms. |
| 3.9 | T.A and D.A for the supervisor in supervisory visit. |

| RESULT 4: IMPROVED ADIQUATE DRUGS SUPPORT AT ALL LEVEL |  |
| --- | --- |
| 4.1 | Logistic supply at all level |

| RESULT 5: : IMPROVED SUPPORTIVE MANAGEMENT ENSURED |  |  |
| --- | --- | --- |
| 5.1 |  | Meeting of the DLS and co-ordination committee. |
| 5.2 |  | Meeting of the DLS and other helping committee ( viyapar sabha & NGO). |
| 5.3 |  | Advocacy meeting. |
| 5.4 |  | Find an active interested partner. |
| 5.5 |  | Help Groups. |
| 5.6 |  | IPC Workshop. |
| RESULT 6: IMPROVED DPMR SERVICES. |  |  |
| 6.1 | Procurement of MCR. |  |
| 6.2 | Self care in villages and colony. |  |
| 6.3 | Training of PHC staff for DPMR services |  |
| 6.4 | Provide appliances. |  |
| 6.5 | HOPE Kit. |  |
| 6.5 | Reconstructive surgery and mobility support. |  |

| RESULT 7:INCREASED AWARENESS AND DECREASED DISCRIMNATION. |  |
| --- | --- |
| 7.1 | School quiz |
| 7.2 | School rally. |
| 7.3 | Folk show |
| 7.4 | Sensitization of VHSC. |

| RESULT 8: PROGRAMME MANAGEMENT ENSURED. |  |
| --- | --- |
| 8.1 | Statistician at district level. |
| 8.2 | Digital camera. |
| 8.3 | Computer to be procured. |
| 8.4 | Telephone and internet facility. |
| 8.5 | Stationary. |
| 8.6 | Electricity . |
| 8.7 | Honorarium to the concerned clerk or district level supervisor looking extra work of the programme. |

BUDGET BREAKDOWN & SUMMARY –

ACTIVITY PLAN.

| S.N | Activities | Responsible staff | Duration & Date | Budget required |  | Fiscal Source |
| --- | --- | --- | --- | --- | --- | --- |
| RESULT 1:IMPROVED CASE DETECTION & REPORTING SYSTEM |  |  |  |  |  |  |
| 1 | Re- orientation training of MO 20 | SLO | 2 days | Honorarium for trainers 2Tx600X2 Rs. 2400/- T.A of tranees 500x20x2 Rs. 20000/- D.A of Tranees 20Tx150x2 Rs. 6000/- Stationary 20Tx50x Rs. 1000/- Tea ,Snaks for tranees 150x20x2 Rs. 6000/- | 3,5400/- | --------- |
| 2 | Re-orientation training of left ANM 177 | DLO | 1 day | Honorarium for trainers 2Tx300 x5 B Rs. 3000/- T.A of tranees 100x177 Rs. 17700/- D.A of Tranees 177Tx100 Rs. 17700/- Stationary 177Tx20 Rs. 3540/- Tea ,Snaks for tranees 100x177 Rs. 17700/- | 59640/- |  |
| 3 | Re-orientation training of pharmacist 30 | DLO | 1 day | Honorarium for trainers 2Tx300X Rs. 600/- T.A of tranees 100x30 Rs. 3000/- D.A of Tranees 30Tx100 Rs. 6000/- Stationary 30Tx20x Rs. 600/- Tea ,Snaks for tranees 100x30 Rs. 3000/- | 13200/- | ----- |
| 4 | ASHA Training | MOIC | 3 hrs | At ASHA meeting | ------- |  |
| RESULT:2 IMPROVED CASE REFRAL . |  |  |  |  |  |  |
| 1 | Referral Slip and formats. | DLO |  |  | 10000/- | DLS |
| 2 | ASHA Incentives | DLO |  |  | 3800/- | DLS |
| 3 | Incentive for cases on completion of Tt. | DLO |  |  | ------- | DLS |
| 4 | Road travel for Pt. to referred center | DLO |  | Actual ticket. VHSC | -------- | DLS |
| 5 | Logistics and stationary | DLO |  | 500 / PHC x 15 | 7500/- | DLS |

| RESULT: 3 IMPROVED MONITORING & SUPERVISION. |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Vehicle |  | DLO |  | POL & Vehicle Repair. |  | 50,000/- |  |  |
| 2 | Quarterly review meeting with M.O. PHI’s |  | CMO & DLO | 1 day | 2500 x 4 |  | 10,000/- |  |  |
| 3 | T.A and D.A for the supervisory visit. |  | DLO | monthly | T.A & D.A. |  | 15,000/- |  |  |
| 4 | Supervisory check list |  | DLO |  |  |  | 10,000/- |  |  |
| RESULT: 4 IMPROVED DRUG SUPPORT AT ALL LEVEL |  |  |  |  |  |  |  |  |  |
| 1 | Logistic supply at all level | DLO |  |  |  |  | ------- |  |  |
| 2 | Supportive medicines | DLO |  |  |  |  | 20,000/- |  |  |
| 3 | Lab Reagents. | DLO |  |  |  |  | 5000/- |  |  |
| RESULT: 5 IMPROVED SUPPORTIVE MANAGEMENT ENSURED. |  |  |  |  |  |  |  |  |  |
| 1 | Meeting of co-ordination committee & NGO Help Group | DLO |  | Twice a year | 5000 x 2 |  | 10000/- |  |  |
| 2 | Advocacy meeting |  |  |  | 5000 |  | 5000/- |  |  |
| RESULT: 6 IMPROVED DPMR SERVICES. |  |  |  |  |  |  |  |  |  |
| 1 | Aids & Appliances | DLO |  |  |  | 3000/- |  |  |  |
| 2 | MCR Footwear | DLO |  | For two laper homes. |  | 3900/- |  |  |  |
| 3 | HOPE kit. | DLO |  | -------- | For every patients. | 15000/- |  |  |  |
| 4 | Reconstructive Surgery. | DLO |  | ----- | 3 x5000 | 15000/- |  |  |  |
| 5 | Blanket / Sweaters | DLO |  | ----- | 20x 600 | 12000/- |  |  |  |
| RESULT: 7 INCREASED AWARENESS AND DECREASED DISCRIMINATION. |  |  |  |  |  |  |  |  |  |
| 1 | School Quiz (4) | DLO |  |  | @ Rs.1500/- Per Quiz x 4 | 6000/- |  |  |  |
| 2 | School rally (4) |  |  |  | @ 2000/; per rally | 6000/- |  |  |  |
| 3 | Folk Show (15) | DLO/BMO |  |  | @ Rs.3000/- Per Show | 45,000/- |  |  |  |
| 4 | IPC Meeting | BMO |  |  | At BDC meeting / Atal adarsh Gram meeting. | 17500/- |  |  |  |
| RESULT :8 PROGRAMME MANAGEMENT ENSURED. |  |  |  |  |  |  |  |  |  |
| 1 | Computer to be procured | DLO |  |  |  | 50,000/- |  | Computer to be procured |  |
| 2 | Telephone and internet facility | Office clerk |  |  |  | 12000/- |  | Telephone and internet facility |  |
| 3 | Stationary | Office clerk |  |  |  | 15,000/- |  | Stationary |  |
| 4 | Honorarium to clerk looking extra work. | Office clerk |  |  |  | 6,000/- |  | Honorarium to clerk looking extra work. |  |

  - IDDCP (Iodine Deficiency Disorder Control Programme).

National Iodine Deficiency Disorders Control Programme is implemented in the state over last four decades. Urinary iodine levels, Salt samples are tested in district Public Health Labs for content of Iodine.  Food and Drugs Administration (FDA) is informed about the results.  With the help of UNICEF, salt manufactures are approached and promoted for iodized salt.  Wide publicity is given on Global Iodine Day. As it is know well, micronutrients have important role in the health status of all of us.  One of the important micronutrients is coupled with an amino acid called thyroxin is synthesized in a butterfly shaped endocrine gland called thyroid gland.  This gland is situated in the front part of neck.

Deficiency of iodine results in wide spectrum of disorders termed as iodine deficiency disorders.  These disorders include loss of IQ by 10 to 15 points, decrease in the activity of all members of society, Mental

retardation, increasing incidence of abortions, congenital abnormalities etc.

Objective:-

- To Reduce Iodine Deficiency Disease in population In District PAURI GARHWAL..

- Surveillance of Goitre cases.

- Supply of iodized salt in place of common salt.

- Health Education & Publicity.

- Laboratory monitoring of iodated salt and urinary iodine excretion.

IODISED SALT CHECKED BY ANM FROM SAMPLES COLLECTED AT HOME.

| YEARS | TOTAL SAMPLE | > 15 PPM | < 15 PPM | ZERO PPM |
| --- | --- | --- | --- | --- |
| 2004-05 | 5879 | 5270 | 607 | 02 |
| 2005-06 | 6188 | 5654 | 534 | 0 |
| 2006-07 | 7286 | 6681 | 605 | 0 |
| 2007-08 | 2650 | 2465 | 185 | 0 |
| 2008-09 | 798 | 770 | 22 | 6 |
| 2009-10 | 948 | 927 | 21 | - |
| 2010-11 | 3490 | 3372 | 118 | - |
| 2011-12 | 2003 | 1949 | 54 | - |

IODISED SALT CHECKED BY ANM FROM SAMPLES COLLECTED AT SHOPS (STOKIST).

| YEARS | TOTAL SAMPLE | > 15 PPM | < 15 PPM | ZERO PPM |
| --- | --- | --- | --- | --- |
| 2004-05 | 1828 | 1557 | 271 | 0 |
| 2005-06 | 2065 | 1837 | 228 | 0 |
| 2006-07 | 1975 | 1731 | 244 | 0 |
| 2007-08 | 860 | 826 | 34 | 0 |
| 2008-09 | 306 | 306 | 0 | 0 |
| 2009-10 | 155 | 155 | 0 | 0 |
| 2010-11 | 556 | 537 | 19 | 0 |
| 2011-12 | 340 | 333 | 7 | 0 |

Strategies and Activities:-

| Iodine Deficiency Disorder Control programme |  |
| --- | --- |
| Activities: | - Health Education & Publicity - IEC through observation of Global 100 Prevention Day on 21st October. - IEC through Electronic media. - IEC through Sensitisation Seminars - Public awareness Camp on IDD - IDD/GOITRE Survey - IDD/Goitre Survey work to be taken in as per Guideline of Govt. of India in phased manner taking help of 1 Medical Colleges of the District. So, 15 Blocks have got to be surveyed within a period of 1 year. - Identify high-risk population. - Establishment of IDD Monitoring Laboratory - As per Govt. of India Guideline - for analysis of Salt Samples and Urine samples, an IDD Monitoring Laboratory. - There is Act for mandatory supplying of the iodize salt in the District. - Improved detection of non iodised salt by worker ( in samples) - Improved detection of non iodised salt by food inspector( in samples) - Improved kit supply for iodine deficiency. - Training to ASHA. Improved case detection of hypothyroidism like symptoms in adults & children in general OPD. |

  - (NPCB )National Programme for control of Blindness.

National programme for Control of Blindness,  include  innovative  approach  for  cataract  management  through  formation  of  cataract identifying  team.  This  team  constitutes  of  multipurpose  health  worker,  religious  leaders  of  the village,  link  person,  community  based  volunteers,  ASHA,  ophthalmic  assistant,  and  supporting  staff. School eye examination is also strengthened for managing refractive errors.

The major causes of blindness are cataract, glaucoma, myopia (refractive error), corneal injury, trachoma and developmental hereditary anomalies. Cataract  or loss  transparency  of  the lens  in  the eye  interfering  with  vision  is  the most important pathological condition of the lens. cataracts  a  major  cause  of  blindness  all  over  the  world.

Facts about Blindness:

  - Rapid increase after 50 years of age

  - Prevalence of blindness higher among the poor & uneducated

  - Higher prevalence among female

  - Higher prevalence in rural & backward areas

Objective:-

- To  achieve  the  maximum  reduction  in  the  prevalence  rate  of  Blindness  in  the  District  through

Optimal utilization of available resources in the district.

- To provide high quality of eye care to the affected population.

- To expand coverage of eye care services to the underserved areas.

- To reduce the backlog of blindness by identifying and providing support for equipment and material and training personnel.

Strategies and Activities:

- Screening for refractive errors & Provision of Spectacles.

- Three Persons are the key persons for the implementation of SES program (Teacher, Ophthalmic Assistant, and Optician).

- Teachers will be given Training for One day by Paramedical Ophthalmic Assistant. Training will include.

  - Lecture Demonstration.

  - Audio Visual Aid.

  - Group Discussion.

  - Question & Answers.

  - Provision of Teachers Kit (E Chart  , Referral Cards, Measuring Tape, Record Register / Forms)

- Teachers will first enlist the targeted students, conduct the actual procedure as per given in the Training, refer the students with referral cards to the nearest PHC/CHC.

- Ophthalmic Assistant.

  - Diagnosis.

  - Prescription of Spectacles.

  - Reference to District Ophthalmic Surgeon if needed.

  - Follow up & Data management.

  - Maintain the register.

- Optician  will  be  selected  from  the  district  and  he  will  be the  key  person who  will supply spectacles with correct prescription in time.

- IEC and EYE health education at all levels to be undertaken.

- Screening of school going children for identification and treatment of Refractive Errors, with special attention in under served areas.

- Camp Approach (Govt and NGO)

- Regularly organize mega eye camp at District Hospital, CHC & ALL PHC of district with the help of NGO's in monthly bases.

- Special camps for IOL cataract surgery at nearest IOL centre Sub-District Hospital.

- Involvement of voluntary organization in various eye care activities.

- IEC activities.

- IEC activities in relation to Cataract surgery.

- IEC and EYE health education at all levels to be undertaken.

- Encouraging for EYE donation.

- Awareness regarding Eye Care, Eye injuries and its prevention.

- IEC material can be prepared on that basis at district level.

- Cataract Surgery.

- Free surgery for cataract cases in rural areas.

- Free transportation for patients of unreached areas.

- Free medicine for all types of eye ailments.

- Free spectacles for post operative care.

- Free spectacles for poor school students.

- All backlog cataract cases would be treated.

- Establishment of one RIO (Regional Institute of Ophthalmology) in one of the medical colleges.

- Training Infrastructure.

- Improvement of quality of eye care services by training of eye care personnel.

- Increased no of cataract surgery by recruiting specialists.

- Training and capacity building of ASHAs to orient them towards Blindness control programme.

- Provision of modern equipments instruments and other commodity assistance by GOI.

- Modern and advanced treatment would be available in a Medical College Hospital.

- Decentralized implementation of the scheme through District Blindness Control Society.

- Special focus on illiterate women in rural areas.

- Besides cataract surgeries other Intra-ocular surgical operations for treatment of Glaucoma, Diabetic, and Retinopathy etc. may also be provided free of cost to the poor patients.

- Public awareness about prevention and timely treatment of eye ailments.

- Participation of community and Panchayat Raj institutions in organizing services in rural areas.

| S.No | Budget Requirement (NPCB) for the year 2013-14 | Physical Target | Funds Required |
| --- | --- | --- | --- |
| Recurring Grant-in-aid |  |  |  |
| 1 | Free Cataract operations @ Rs. 750/- per case (30% of the given target by Govt. Sector ) | 1170 | 877500.00 |
| 2 | Free Cataract Operation for NGO,s (@ Rs. 750/- per case (40% of the given target by NGO,s) | 1560 | 1170000.00 |
| 3 | Payment for ASHA @ 175 per Operated case (as per GOI norms) | 300 | 52500.00 |
| 4 | Others Eye Diseases ( Glaucoma, Diabetic Retinopathy, Keratoplasty & Childhood Blindness ) ( @ 1000/- as per GOI norms) | 50 | 50000.00 |
| 5 | School Eye Screening Programme (Free Spectacles @ 200/- per Spectacles for poor students) | 800 | 160000.00 |
| 6 | School Teachers Training @ 250 per Teacher | 250 | 62500.00 |
| 7 | IEC Activities (13 Districts) - Eye Donation Fort Night (25th Aug to 8th Sept.) - World Sight Day ( 2nd Thursday of OCt. ) |  | 250000.00 |
| 8 | Recurring Assistance for District Health Societies (DBCS) - Honorarium to member secretary @ 2000/- per month - Accounts Assistant part time @ 1500/- per month - TA/DA to staff/ POL and vehicle maintenance/ Stationary & Consumable/ Quarterly Review Meeting, Contingency, hiring of vehicle etc. |  | 24000.00 10000.00 145000.00 |
| 9 | Miscellaneous Expenses |  | 15000.00 |

| Non Recurring Grant-in-aid |  |  |  |
| --- | --- | --- | --- |
| 1 | For Vision Centers @ Rs. 50000/- per center for 50,000 population | 3 | 150000.00 |
| 2 | Procurement of Ophthalmic Equipment (PHACO Machine ) | 0 | 0 |
| 3 | Procurement of Operating Microscopes | 1 | 200000.00 |
| Total Grant-in-aid |  |  | 3302000.00 |

f. (IDSP ) Integrated Disease Surveillance Project.

The Government of India is initiating a decentralized, state based Integrated Disease Surveillance Project (IDSP) in the country in response to a long felt need expressed by various expert committees. The project would be able to detect early warning signals of impending out Breaks and help and initiate an effective response in a timely manner. It is also expected to provide essential data to monitor progress of on going disease control programs and help allocate health Resources more optimally. Current advanced to technology is to be used for collecting data for different diseases. It is proposed to provide network connectivity initially up to District level. Computers for data entry and Receiving inputs from the district level would be available.

Integrated Disease Surveillance Project Funded by the World Bank is being implemented since November 2004 with the objective of strengthening surveillance system with various Communicable Diseases and Risk Factor of Non-Communicable Diseases. One of the important components of the Project is to use Information Technology and Communication Technology in data management, analysis and rapid response in case of impending outbreaks. To strengthen transmission of data, the Ministry of Health & FW and Indian Space Research organization (ISRO) have agreed to cooperate in providing satellite linkage for various activities under World Bank funded Integrated Disease Surveillance Project. ISRO would provide adequate bandwidth on one of its satellite, EDUSAT for this Project. This satellite has 5 regional beams and one national beam covering the entire country. This linkage would be available for the following activities.

- Data Transmission for Integrated Disease Surveillance.

- Distance Training Programmers for various National Health Programmes.

- Tele-conferencing to review various schemes with the States.

- Networking a nation-wide information highway for the Health Sector.

The network established under EDUSAT Project would be to connect Central Surveillance Unit located at NICD, Delhi with a sub-hub in Nirman Bhawan, the Head Quarter of Dte.GHS and Ministry of Health. There will be 800 Satellite Interactive Terminals throughout the country covering all states and districts surveillance teams:-

 All States & District Surveillance Units

 National & State level Medical and Health Institutions.

 Reference Public Health Laboratories.

 Medical Colleges.

Strengths of IDSP

• Functional integration of surveillance components of vertical programmers

• Reporting of suspect, probable and confirmed cases

• Strong IT component for data analysis

• Trigger levels for gradated response

• Action component in the reporting formats

• Streamlined flow of funds to the districts

Objective:-

- Improve the information available to the government health services and private health care providers on a set of high-priority diseases and risk factors.

- Improving the on-the ground responses to such diseases and risk factor.

- To establish a district based system of surveillance through Information and communication technology (ICT) for communicable and non-communicable diseases.

Especially the project aims:-

To establish a decentralized state based system of surveillance for communicable and non-communicable diseases so that timely and  effective public health actions can be initiated in response to health challenges in the country at the  state and national level to improve the efficiency of the existing surveillance  activities of disease control  programs and facilitate sharing of relevant information with the health administration community and other stake-holders so as to detect disease trends over time and evaluate control strategies.

Strategies and Activities

- Up gradation of Laboratories.

- Renovation & furnishing of Labs.

- Supply of Lab Equipments.

- Lab Material and supply.

- Information Technology and Communication.

- Computer Hardware & Office Equipments.

- Software for Surveillance.

- Leasing of Wide Area Networking.

- Use of established at National Institute of Communicable Disease and Linkage with the State.

- Human Resource & Development.

- Consultant/Contract Staff.

- Training.

- Information, Education & Communication at the District Level.

- Decentralization of Surveillance activities.

- Peripheral Surveillance Units –CHCs.

- District Surveillance Units.

- State Surveillance Units.

Information flow of the weekly Data

surveillance system

Sub-centres

P.H.C.s

C.H.C.s

Dist. hosp.

Programme

officers

Pvt. practitioners

D.S.U.

P.H. lab.

Med. col.

Other Hospitals:

ESI, Municipal

Rly., Army etc.

S.S.U.

C.S.U.

Nursing homes

Private hospitals

Private labs.

Corporate

hospitals

- For Regular Surveillance and epidemic detection and control.

- To carry out the Surveillance on S, P, L Format on weekly basis.

- To give feedback on the information received to all the reporting units as mentioned on the above formats and action taken.

- Report on weekly basis i.e from Monday to Sunday of every week.

- Analysis of Data. -  Detection of Early Waning signals.

- To detect Epidemic and Outbreak and control on Weekly basis.

A functional vision of surveillance

1. Collect and

transmit data

2. Analyze

data

3. Feedback

information

4. Make

decisions

All levels use

information

to make

decisions

Present Situation:

1. Manpower:

Contractual staff at District Surveillance Unit is designated. The detail list is as follows:

| S.no | Manpower | Present Situation |
| --- | --- | --- |
| 1 | Epidemiologist | Vacant |
| 2 | Microbiologist | 1 |
| 3 | Data Manager | 1 |
| 4 | Data Entry Operator | 1 |

2. IT & EDUSAT:

IT & EDUSAT is well established but not functioning in district Pauri.

3. Total Reporting Units

- Reporting Units in form S -  136

- Reporting Units in form P -   21

- Reporting Units in form L -   21

| Total no of Reporting Units in different form |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Form S | Form P |  |  |  |  |  |  | Form L |  |  |  |  |  |
| Subcenter | PHC | APHC | CHC | Distt. Hospt. | Sub District Hospital/ Medical College | Private | Total | PHC | CHC | Distt Hospt. | Sub District Hospital/Medical College | Private | Total |
| 136 | 10 | 1 | 5 | 1 | 3 | 1 | 21 | 10 | 5 | 1 | 3 | 2 | 21 |

Number and percentage of blocks providing monthly surveillance reports on time for S P L Form

| Number and percentage of blocks providing monthly surveillance reports on time for Form S in 2012 Week : 1 TO 46 (Total Weeks : 46) |  |  |  |
| --- | --- | --- | --- |
| Total no of reporting units in form S | No. of units reported ≥ 80% Time | No. of units reported between 50%-80% Time | No. of units reported <50% or Null Time |
| 136 | 125 | 8 | 3 |

| Number and percentage of blocks providing monthly surveillance reports on time for Form P in 2012 Week : 1 to 46 (Total Weeks : 46) |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total No of RU's | PHC |  |  |  | Govt. Hospital/ID Hospitals/CHC/Medical College |  |  |  | Private Sector |  |  |  |
|  | Total no. of Rus | No. of units reported ≥ 80% Time | No. of units reported between 50%-80% Time | No. of units reported <50% or Null Time | Total no. of Rus | No. of units reported ≥ 80% Time | No. of units reported between 50%-80% Time | No. of units reported <50% or Null Time | Total no.of Rus | No. of units reported ≥ 80% Time | No. of units reported between 50%-80% Time | No. of units reported <50% or Null Time |
| 21 | 11 | 11 | 0 | 0 | 9 | 9 | 0 | 0 | 1 | 1 | 0 | 0 |

| Number and percentage of blocks providing monthly surveillance reports on time for Form L in 2012 Week : 1 to 46 (Total Weeks : 46) |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total No of RU's | PHC(Lab) |  |  |  | Govt. Hospital(Lab.)/ID Hospitals(Lab.)/CHC(Lab.)/Medical College(Lab.) |  |  |  | Private Sector(Lab) |  |  |  |
|  | Total no. of Rus | No. of units reported ≥ 80% Time | No. of units reported between 50%-80% Time | No. of units reported <50% or Null Time | Total no. of Rus | No. of units reported ≥ 80% Time | No. of units reported between 50%-80% Time | No. of units reported <50% or Null Time | Total no.of Rus | No. of units reported ≥ 80% Time | No. of units reported between 50%-80% Time | No. of units reported <50% or Null Time |
| 21 | 10 | 10 | 0 | 0 | 9 | 9 | 0 | 0 | 2 | 2 | 0 | 0 |

4. Name of diseases for which test is done at Priority Lab Pauri.

| S. No | Name of Disease Test | Test recommended by IDSP | Lab Status | Remark |
| --- | --- | --- | --- | --- |
| 1 | Cholera | - Presumptive Identification by HDP - Vibrio Cholera culture - Strain Confirmation | Yes Yes Yes | - |
| 2 | Typhoid Fever | - Widal Test - Blood culture - Typhidot | Yes Yes Yes | - |
| 3 | Shigella dysentery | - Bacterial Culture | Yes | - |
| 4 | Water Testing | - H2S Test | Yes | During outbreak only |
| 5 | Diptheria | - Diptheria culture | Yes | - |
| 6 | Hep B | - HBsAg Card Test | Yes | - |

| S.no | Equipment requirement for Priority Lab | Requirement |
| --- | --- | --- |
| 1 | Elisa Reader | 1 |

Priority Lab Pauri requires one Elisa reader so that various test for other diseases can be performed at lab itself.

| 5. Outbreak during 2012 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sr. No. | Disease/ Illness | Affected Area |  | Total Population | Date of start of outbreak | No. of Cases | No of Deaths | Comments |
|  |  | Block | Village |  |  |  |  |  |
| 1 | Vomiting & Bacillary Dysentery (Bloody Dysentery) | Thalisain | Dungri, Kundil, Rikholi | 1254 | 02.05.12 | 225 | 0 | It was basically due to unhygienic conditions, contamination of drinking water tanks and leakage in various pipe lines. |
| 2 | Vomiting, Loose Motion & Swelling in entire body. Loss of appetite & Anaroxia. (Trichinosis) | Kot | Sirala, Payal Gaon | 523 | 04.05.12 | 55 | 0 | It was basically due to the consumption of uncooked infected raw flesh of wild pig. |

6. Operational Expenses Rs. 5,62,000/-

- Office Expenses

For the establishment charges for running the offices includes the expenditure for Telephone Charges, Office Stationery, DA for officers/staff engaged under IDSP, Consumable Items, Miscellaneous including Contingencies maintenance cost of computers/printers/Photostats, IT Equipments and Lab Equipments.

- Broadband Expenses

VPN Broadband Connection with Sulabh Telephone and internet facility has been installed in District  Surveillance Unit under IDSP project based on the centralized advice note issued by NTR to GM(BD)s of the circles, as per the procedure of E-governance Broadband connection. These connections are working at district places.Broadband expenses has to be met by the District Surveillance Units.

- Review Meetings

Sensitization workshops and Review Meetings for District Surveillance Officers, PIED Cell Coordinator, Epidemiologist, Microbiologist, Data Manager and Data Entry Operator to strengthen the activities of IDSP.

- Mobility Support/Field Visits

Intensified supervision and monitoring of Peripheral from District level. The POL charges, Travel Cost, Maintenance and Hiring of Vehicle charges etc.

- Consumables for Kits for Identified Priority District Labs

Consumables for One District Priority Labs (Distt. Hospital Pauri) and Consumables, Diagnostic Kits, Various Lab Consumables including Glass wares Etc.

7. Staff Salary Rs. 1512000/-

- Remuneration of Contractual staff

The Government of India initiated a decentralized, state based Integrated Disease Surveillance Project (IDSP) in the country from 2004.         From 2004 to 2012 staff salary was incremented only once and that increment was quite minimal. No salary increment has been done till date. Salary remuneration should be revived.

8. IEC-BCC Activities Rs. 50,000/-

IEC/BCC activities will be undertaken for enhancing awareness, preparedness and  empowering community to take informed decisions in respect of prevention & control of diseases. These activities helps to create awareness in behavior change of diseases around them.

9. Budget proposed for 2013-14

| Sl.No. | Activity | Unit Cost | Physical Targets | Required fund under NRHM |
| --- | --- | --- | --- | --- |
| 1 | Operational Cost |  |  |  |
| 1.1 | Mobility Support/ Field Visits | 10000.00 | 15 Blocks | 150000.00 |
| 1.2 | Lab Consumables | - | - | 200000.00 |
| 1.3 | Review Meetings | 10000.00 | 4 Meeting | 40000.00 |
| 1.4 | Broadband Expenses | 3000.00 | 12 Months | 36000.00 |
| 1.5 | Telephone Expenses | 3000.00 | 12 Months | 36000.00 |
| 1.6 | Collection and transportation of samples | 3000.00 | 12 Months | 36000.00 |
| 1.7 | Stationary and other Office Expenses like Feed back,Printer and Xerox Machine Catridges etc | 10000.00 | 12 Months | 100000.00 |
|  | Sub Total |  |  | 598000.00 |
| 2 | Human Resources |  |  |  |
| 2.2 | Remuneration of Epidemiologists | 40000 | 12 Months | 480000.00 |
| 2.4 | Remuneration of Microbiologists | 40000 | 12 Months | 480000.00 |
| 2.5 | Data Managers | 28000 | 12 Months | 336000.00 |
| 2.6 | Data Entry Operators | 18000 | 12 Months | 216000.00 |
|  | Sub Total |  |  | 1512000.00 |
| 4 | Procurements |  |  |  |
| 4.1 | Procurement -Equipments |  |  | 100000.00 |
| 8 | IEC-BCC Activities |  |  | 50000.00 |
|  | Sub Total |  |  | 150000.00 |
|  | Total |  |  | 3580000.00 |

11. INTER-SECTORAL CONVERGENCE:

Convergence and coordination with other departments engaged in improving health and quality of life of women and children is essential for successful implementation of interventions envisaged under RCH II. District Magistrate is the chairperson of district level committees that are interested with project implementation monitoring and review projects implemented by most social and developmental departments at the district level. Similarly district magistrate is the ex-officio chairperson of district RCH society. District level convergence workshops involving all connected departments are held from time to time to ensure proper convergence and cooperation in smooth implementation of project activities.

The Convergence is recognized as the key for implementing the health programme under National Rural Health Mission .

Convergence with Education Department:-

- School teachers are being involved in school health programmes especially their assistance is taken in examination of Children. Screening of children for health problems, vision defects Etc.

- Children. Identification of health problems among school children and in treatment aspects.

- The school teachers are involved in Pulse Polio campaign and also in Census.

- IEC activities.

- School health Education

- Health and Water Sanitation Committee.

Convergence with Women and Child Welfare Department:-

- Anganwadi workers are responsible for identification of children with malnutrition.

- Helping ANM in immunization of children and in community mobilization.

- Involved in other maternal and child health care interventions like creating awareness on adolescent health issues i.e. age at marriage, nutrition and prevention of Anaemia.

Convergence with Panchayat Raj Institutions:-

- Gram Panchayat are being involved in preparing~ implementation and monitoring of panchayat level health action plans through health committees formed at the panchayat level.

- They will be awarded incentives on achieving 95 % institutional deliveries. 99 % coverage of full immunization of children against all vaccine preventable diseases and 100% registration of antenatal cases, birth and deaths.

- Gram panchayats are responsible. For village sanitation and .protected. Water supply.

- Gram Panchayats are being involved in maternal and child. Health care interventions and family planning.

- PRI’s Meeting should be held once every three month in District Level.

- PRI’s Meeting should be held once every Two month at Block Level.

- PRI’s Meeting should be held once every month in Village Level.

The services are being implemented through a network of PHCs. Mobile Medical Units, Government Dispensaries, Civil Hospital, sub-centers and other health care institutions.

Convergence with Public Health department:-

- Provision of safe drinking water to all households. Presently 2,853 Villages has safe drinking water facility.

- Periodic Chlorination Health facilities.

- Covering all open drains and puddles of water.

- Notification of diseases in villages.

Rural Development Department:-

- Formation of a Core group at the gram Panchayat level for joint action.

- Roads, Maintenance of buildings, Electricity and water supply are the domain of the rural development.

- School Sanitation and IEC are important components of Total Sanitation Campaign.

Partnership with AYUSH department:-

Under Ayush there are: 50 Government Ayurvedic Dispensaries and 67 State Allopathic Dispensary Special Centre and 7General Homeopathic Dispensaries.

- For outreach and coverage of areas not covered by MOs.

- Joint training in Surveillance, Joint meetings.

- Joint planning for BCC.

- Joint Review and joint planning

- Provision of medicine kits

- DOTS providers

- Diseases Surveillance

ICDS projects:

- Training for counselling clients,

- Provision of spacing methods including oral pills, condoms, LAM and SDM and community mobilization.

- Convergence of services at the grassroots would ensure increasing the access to and demand for services.

- Joint sector meetings, block and district meetings.

Convergence with other Departments:

In addition to the above mentioned departments" cooperation of other departments like rural water supply department, revenue departments and municipal authorities are obtained in prevention and control of gastro-enteritis and diarrhoeas in the district.

Objective:-

- Providing Primary and basic quality health care services at the village level.

- Providing quality RCH services.

- Optimal utilization of RCH services by community especially women.

- Empowering women to facilitate them to seek and demand quality RCH services.

Strategies and Activities:

- Strengthening the various Committees and Societies.

- Joint workshops for Planning and Review at all levels.

- Orientation programmes

- Monthly meetings

- Strengthening the VHND days.

- Wide participation of all the sectors in preparation of the community and in the actual activities, in health education

- Each Wednesday during Immunization sessions joint orientations by all sectors and problem solving for each of the sectors.

- Joint action for various issues.

- Joint Action for Sanitation, provision of safe water, provision of services and personnel at facilities.

- Joint efforts for education of the girls, improving the sex ratio, raising age of marriage, improving the nutritional status, identifying the correct BPL families, income generation.

- Joint CNAA to determine the needs and thereby developing the plans jointly.

- At the monthly meetings of the Civil Surgeon the officers of all the departments should come.

- Annual action Plans to be developed jointly through meetings at the village, Gram Panchayat, Sector and culminating in Block workshops and District workshops.

12. Infrastructure:

Infrastructure Development

At this time there are 1 District Hospital Male & Female, 2 Combined Hospitals, 5 CHCs, 10 Block Level PHCs, 22 Add. PHCs 67 State Allophatic Dispensaries and 218 Subcentres are functioning in the District. In the year 2007-08,               73 Satellite Subcentres were sanctioned but they are not functioning due to lack of staff.

In above facilities some units are functioning in Govt. Building, some are under construction and some units are rented building.

Details given below –

| S.No. | Name of Facility | Total No of Facilities | Functioning in Govt. Building | Under Construction |
| --- | --- | --- | --- | --- |
| 1 | D.H. Male | 1 | 1 | - |
| 2 | D.H. Female | 1 | 1 | 1 |
| 3 | Comb. Hospital | 2 | 2 | 1 (Satpuli) |
| 4 | CHCs | 5 | 5 | 7 ( Khirsu, Rikhnikhal Kot,Pokhra, Naugaunkhal, Chakisain, Yamkeshwar.) |
| 5 | Block Level PHCs | 10 | 10 | - |
| 6 | Add. PHCs | 22 | 16 | 4 (Paithani Bungidhar, Siroli & Lalitpur) |
| 7 | Rural Female Hospital | 8 | 1 | 7 |
| 7 | State Allophatic Dispensaries | 67 | 35 | 12 |
| 8 | Subcentres | 218 | 73 | 29 |
| 9 | Transit Hostel | 1 | 1 | - |
| 11 | Postmartum House | 3 | 3 | 1 (Approved for new) |

Proposal for 2013-14 for strengthening of Infrastructure through NRHM –

- In the present time there is functioning ANM Training Centre at Khirsu but hostel capacity of Training Centre is available for 60 trainees. For strengthening of Subcentres there is the extra requirement of 30 bedded hostel at ANM Training Centre. If 30 bedded hostel is sanctioned there will be the requirement of Kitchen Mess for 60 trainees also by construction of 1 extra Dining Hall. So for strengthening of ANM Training Centre there will be requirement of100 Lakh Rupees.

- In the present time there are functioning 218 Subcentres in the District and 73 Subcentres are functioning in Govt. Building as mentioned above. In above Subcentres only 20 Subcentres have Labour & Waiting room. Proposed 15 Subcentres for extension of Labour & Waiting room in existing Subcentre buildings in year 2013-14, so there will be required 60 Lakhs Rupees.

- In the present time CHC Thalisain is functioning and building capacity is also complete as per norms of CHC. In the year 2009-10 CHC Thalisain is upgraded as FRU. So it is proposed to have 6 OPD Rooms for Medical Officers, 4 Medical Officers Residence, 6 Type-2 Residence for Staff nurses and Para medical staff and 2 Garage for Ambulance whose approximate requirement of fund is 150 Lakhs.

- In the present time CHC Bironkhal is functioning as per norms of FRU. In Financial year 2013-14 it is proposed 4 Medical Officers Residence, 6 Type-2 Residence for Staff nurses and Para medical staff. Whose approximate requirement of fund is 100 Lakhs.

- District Hospital Male and Female are functioning in government building but there is need of Hostel for Staff nurses due to the damage of old hostel. Therefore the proposal for demolition and reconstruction is required. Para medical staff quarters are also proposed for the next financial year. So in the year 2013-14 there is proposal for nurse’s hostel for 12 staff nurses and six type 2 residences for other Para medical staff. Whose approximate requirement of fund is 150 Lakhs.

13. BIO- MEDICAL WASTE MANAGEMENT

Situation Analysis /Current Status

As per the Bio-Medical Waste Rules, 1998, indiscriminate disposal of hospital waste was to be stopped with handling of Waste without any adverse effects on the health and environment. In response to this the Government has taken steps to

ensure the proper disposal of Biomedical waste from all Nursing homes, hospitals, Pathological labs and Blood Banks.

The District Health Officer is the Nodal Person in each district for ensuring the proper disposal of Biomedical Waste.

For effective disposal of Biomedical waste in the district; Trainings to the personnel for sensitizing them, Pits. Segregation of Waste is taking place though Separate Colour Bins/containers it has to be done more systematically. Proper Supervision is lacking.The treatment (incineration) of waste is suppose to handled by a company selected at the State level but till date the company has not been selected. There is a monopoly of these companies so their charges are high.

Objectives

1. Stopping the indiscriminate disposal of hospital Waste from all the facilities

2. Ensuring proper handling and disposal of Biomedical Waste in each Facility

Strategies

1. Capacity Building of personnel

2. Proper equipment for the disposal and disposal as per guidelines

3. Strict monitoring and Supervision

Activities

1. Review of the efforts made for the Biomedical Waste Interventions

2. Development of Microplan Plan for each facility in District & Block workshops

3. Capacity Building of personnel. Biomedical Waste management to be part of each training in RCH and IDSP

4. Proper equipment for the disposal Installation of the Separate Colour Bins/containers and Plastic Bags

5. Segregation of Waste as per guidelines

6. Partnering with Private providers for waste disposal

7. Proper Supervision and Monitoring Formation of a Supervisory Committee in each facility by the MOs and the Supervisors

14. PROCUREMENT AND LOGISTICS:

Availability of right product at right time and place in appropriate quantity and acceptable quality is essential to provide uninterrupted services to clients. More often than not procurement of products gets delayed not because of lack of financial resources but due to absence of transparent systems and procedures. In the recent study conducted under UAHFWS huge wastage of products, abundant availability of products at some health units and shortage in other units, and date expired products are observed which manifest the inefficient logistics systems in place. Considerable amount of resources could be conserved and utilization of resources could be improved if efficient logistics system is in place.

Computerized system would provide information on all aspects including medicines and contraceptives, without any delay. Development of computerized LMIS and training of personnel for its effective use at various levels required external assistance and support.  Strengthening LMIS is already under-way as part of the USAID technical assistance to Uttarakhand.

| Logistics Elements | Description |
| --- | --- |
| Availability of a dedicated District warehouse for health | Not available |
| Stock outs of any vital supplies in last year | . |
| Indenting Systems (from peripheral facilities to districts) |  |
| Existence of a functional system for assessing Quality of Vaccine | Cold chain maintained temperature of ILR/Deep Freezer-twice a day. Colour code observed in case of polio vaccine quality |

Objective:

- Development of a Scientific Warehouse system.

- Expand Cold Chain Reach and Improve Performance.

- Uninterrupted and timely supply of quality drugs for the district/facilities during the year 2009-10.

- Transparency in purchasing of Drugs and medicine

Strategies and Activities:

- Developing a Warehouse

  - Construction of a scientific Warehouse.

  - Appointment of an agency for Operationalization of the Scientific Warehouse.

- Capacity building of the personnel for stores and also record keeping.

- Fulfilling all the Vacant Positions in the district Pauri.

- In Emergency Outsourcing with other districts.

- Improve supply of Vaccines / Logistics.

  - Procure the vaccines and AD syringes with a buffer stock of 3 months.

  - Monitor utilization of vaccine and AD syringes at each level.

- Computerization of all the stocks.

- Procurement of software and computer hardware for the Warehouse from TNMSC.

- Training of personnel.

- Expand Cold Chain Reach and Improve Performance.

  - Supply of Logistics i.e. ILR/ DF/Voltage Stabilizers Vaccine Carries/ ICE Packs/ Thermometers to newly sanctioned peripheral health institutions.

  - Maintenance of Temperature logbooks and their regular supervision   by Medical Officers.

  - Refresher training and re training of Para medicals involved in Cold chain Maintenance.

  - Prompt repair of Cold Chain Equipments.

  - Supply solar operated ILR/ Refrigerators in hard to reach areas.

- To develop proper need base procurement plan of drugs.

- List of all drugs and logistic has been prepared in time (Forecasting).

- Supply of drugs and medicine well in time.

- Availability / Supply of drugs and medicine to all health facilities as per their demand.

- Advertisement & Tender process well in time.

15. MONITORING AND EVALUATION:

Monitoring and Evaluation is one of the important functions of health manager to implement the programme.  The regular and timely tracking of the activities enabled the manager to initiate the midcourse corrective measures. The broad activities under Monitoring and Evaluation are record keeping, reporting, processing, analysing, use and feedback of information for providing an effective momentum to the programme.

Monitoring in aspect of the programme is not happening effectively and regularly. Each officer and the CHC Incharges, MO PHCs are supposed to make regular visits and monitor the progress and check on the activities and also the data provided by the ANMs. The reports have to be submitted and discussed in the monthly review meetings at all the forum.

The District Health Society is not monitoring the progress and neither are the committees at the Block and Gram Panchayat levels. No proper Check-lists exist for monitoring. Also analysis is not done of the visits and any data collected

No Verbal Autopsies (Maternal, Neo-natal, Infant & Child Death audits) are carried out any levels.

There is no system of concurrent Evaluation by independent agencies so that the district officials are aware regarding the progress of programme.

Objective:

- Effective Monitoring and Evaluation system in Place by 2013-14.

Strategies and Activities:

- Developing the system for visits, reporting and review.

  - Fixing the dates for visits, review meetings and reports.

  - Software for the checklist and entry of the findings in the checklist.

  - Each official and PHC MO to make at least 5% facility visits and also of the villages

- Developing a system of Concurrent Evaluation.

  - Concurrent Evaluation by independent agency of selected villages in the district every 6 months.

  - Mobility for monitoring at all levels and with the use of district monitors.

  - Quality assessment of 20% of health institutions each year.

- Develop, improve and Update HMIS to meet the requirements of Managers at District level.

- Train all level staff in the collection and use of database on the planned indicators.

- Appointment of Block level Statistical Assistants.

- Block Level Managers should visit at least 3 subcenter/APHC/SAD monthly basis.

- Specific arrangements to be made for availability of logistic at health service delivery point through proper time-to-time monitoring evaluation and supervision.

- Conduct regular epidemiological tracking (morbidity & mortality) from diseases.

- Monitoring at Village Level by Following Tools

- Village Health Plan.

- Village Health Register.

- Records of the ANM.

- Village Health Calendar.

- Infant and maternal death audit.

- Monitoring Block Level by Following Tools

- PHC and CHC records.

- Block Health Plan.

- Quarterly feedback from village and PHC Health Committees.

- Periodic assessment of the existing structural and functional deficiencies.

- Monitoring CHC/PHC/Subcenter and accordance to their performance reward of Excellency should be given.

16. BUDGET ABSTRACT:

ROP

Thanks to all supporting unit